## OVERALL WO
No. | Natif. No | Item No. | No. WO | Description | Area | SMS / BOQ |  | CRO |  | Total Progress |  | Devisiasi |  | Req
Remark
[6 empty] | SMS Type | Value | Number | Value | % | Value | % | Value
HCA 2019,2020 & 2021
1 |  | 180664/H | 4197884 | HVB-to HZA at M1 Area, Perform Assistance for Gathering Line Inspection (CeRMAT 561180) (Cat-2) | HCA | Estimate | 23050432 | 4200131376 | 23050432 | 100 | 23050432 | 0 |  |  | Job Completed
2 |  | 180188/VH | 7242140 | HX from relief and PSV's to pit, Perform Site Clearing on High vegatation (Cat-2) | HCA | Estimate | 16319175 | 4200131388 | 16319175 | 100 | 16319175 | 0 |  |  | Job Completed
3 |  | 190178/VH | 4203526 | M3 PIT Area, Perform Site Trimming (Cat-2) | HCA | Estimate | 16319175 | 4200131393 | 16319175 | 100 | 16319175 | 0 |  |  | Job Completed
4 |  | 190204/VH | 4203737 | HDL-IV, Perform Site Clearing on High Vegetation for Inspection Access (Cat-2) | HCA | Estimate | 38078075 | 4200131381 | 38078075 | 100 | 38078075 | 0 |  |  | Job Completed
5 |  | 180793/VC | 4199362 | CPA, Repaire IST Tower Bridge (Cat-1) | HCA | Estimate | 214827421.2 | 4200132011 | 214827421 | 86.9072 | 186700599.0262 | -13.0928 |  |  | Job Completed | Deductional
6 |  | 180863/VC | 4200372 | Repair CPA SWGR Roof Leaking During Rain | HCA | Estimate | 65589440 | 4200132475 | 50266907 | 100 | 50266907 | 0 |  |  | Job Completed
7 |  | 180454/VC | 4194989 | CPA, Perform site clearing / triming mangrove along CPA gang way, HGL-HEOR and API area (Cat-1)Routine site clearing Site Trimming at CPA Area. | HCA | Estimate | 43517800 | 4200132009 | 43517800 | 100 | 43517800 | 0 |  |  | Job Completed
8 |  | 190020/VC | 4201941 | CPA, Oil boom Storage jetty-2 P/F,Missing some roof, missing wooden floor & Heavy Corrodade Broken on Handrail & Handrail support Repair (Cat-1) | HCA | Estimate | 84973428 | 4200131868 | 84973428 | 71.7092 | 60933805.6 | -28.2908 |  |  | Job Completed | Deductional
9 |  | 180821/VHB | 4199525 | HDB, Revamping Mobile 1 Shelter (Cat-2) | HCA | Estimate | 265482500 | 4200131886 | 265482491 | 100 | 265482491 | 0 |  |  | Job Completed
10 |  | 180008/VHB | 4188292 | HDB, repair shoreline helipad area (Cat-2) | HCA | Estimate | 1948152984.75 | 4200131396 | 1948152984.75 | 92.5559 | 1803131468.9988 | -7.4441 |  |  | Job Completed | Deductional
11 |  |  | 4195225 | Install Turbin Ventilator at WLC/WIN Workshop | HCA | Estimate | 39122625 | 4200132442 | 39122625 | 100 | 39122625 | 0 |  |  | Job Completed
12 |  | 180267/VHB | 4191874 | HBD WLI WorkShop, Repair leaking Roof / gutter (Cat-2) | HCA | Estimate | 41346220 | 4200131394 | 41346220 | 66.9693 | 27689260 | -33.0307 |  |  | Job Completed | Deductional
13 |  | 180006/VH | 4188290 | HDB, Provide & Install new fire box fire water line Handil Base (Cat-2) | HCA | Estimate | 25482491 | 4200132057 | 25025550 | 90.5831 | 22668928.18 | -9.4169 |  |  | Job Completed | Deductional
14 |  | 190219/VHB | 4203950 | HDB, Repair Road Batch IV (Last Point) | HCA | Estimate | 701393988.75 | 4200132290 | 701393988.75 | 90.0375 | 631517870.7 | -9.9625 |  |  | Job Completed | Deductional
15 |  | 190321/VHB | 4205369 | HBD,Install Some Concrete Fondations FWL (Cat-2) | HCA | Estimate | 36190475.19 | 4200132438 | 36190475.19 | 95 | 34380951.43 | -5 |  |  | Job Completed | Deductional
16 |  | 190324/VHB | 7244894 | HL Relief to Pit, Assist Piping CST for Excavation | HCA | Estimate | 6029475 | 4200132293 | 6029475 | 100 | 6029475 | 0 |  |  | Job Completed
17 |  | 190493/VH | 4208056 | HZA - 410/501, Site Clearing for New Cluster | HCA | Estimate | 51446400 | 4200133254 | 51446400 | 100 | 51446400 | 0 |  |  | Job Completed
18 |  | 190511/VH | 4208291 | HBA-276(HD5-25),Perform Site Trimming | HCA | Estimate | 50589195 | 4200133929 | 50589195 | 100 | 50589195 | 0 |  |  | Job Completed
19 |  | 190506/VH | 4208208 | HJ-510/524,Site Trimming Access to Burn Pit | HCA | Estimate | 32355775 | 4200134009 | 32355775 | 100 | 32355775 | 0 |  |  | Job Completed
20 |  | 190663/VHB | 4210339 | HJ-510, Excavation Bundwall Burn Pit for Access 8 Inch Relief Line | HCA | Actual | 2966800 | 4200134530 | 2966800 | 100 | 2966800 | 0 |  |  | Job Completed
21 |  | 190661/VHB | 4210297 | HBD, wather Station Relocation (Cat-2) | HCA | Estimate | 35525345 | 4200134690 | 35528345 | 100 | 35528345 | 0 |  |  | Job Completed
22 |  | 190672/VC | 4210373 | CPA office, Cut All The Trees in Front of the CPA Office | HCA | Estimate | 33350625 | 4200134760 | 33350625 | 99.1768 | 33076075 | -0.82322 |  |  | Job Completed | Deductional
23 |  | Sub 1971/VC | 4211001 | CPA Walkway to Flare M-615/620, Site Trimming for access install anode | HCA | Estimate | 26680500 | 4200135069 | 26680500 | 81.7608 | 21814185 | -18.2392 |  |  | Job Completed | Deductional
24 |  | 190703/VHB | 4210824 | HDB, Clean Up Ditch Beside Runway (Cat-2) | HCA | Estimate | 240190566 | 4200135491 | 231099366 | 100 | 231099366 | 0 |  |  | Job Completed
25 |  | 190255/VC | 4204477 | Site Triming for INSP. Access, Gas Piping V6010 to TEG & X8990 Pilot | HCA | Estimate | 25119245 | 4200135070 | 25119245 | 100 | 25119245 | 0 |  |  | Job Completed
26 |  | 190815/VH | 4212906 | HLA-HLB; Remove falling tree above pipe | HCA | Actual | 3939125 | 4200135890 | 3939125 | 100 | 3939125 | 0 |  |  | Job Completed
27 |  | 190890/VH | 4214581 | HLB-176, Perform Site trimming (Cat-2) | HCA | Estimate | 75313950 | 4200136933 | 75313950 | 90 | 67782555 | -10 |  |  | Job Completed | Deductional
28 |  | 180741/VH | 4498510 | HAB Switch Gear, Replace False Floor | HCA | Estimate | 294621229.2 | 4200132478 | 294621229.2 |  |  | -100 | -294621229.2 |  | Waiting Schedule
29 |  | 180141/VHB | 4189786 | HDB, created shelter for CCU welding maintenance (Cat-2) | HCA | Estimate | 2361712851 | 4200132758 | 2361712851 | 95.4349 | 2253899196 | -4.5651 |  |  | Job Completed | Deductional
30 |  | 190339/VHB | 4205622 | HDB Infront of WLC-WIN Workshop, Install Additional Shelter (Cat-2) | HCA | Estimate | 251882480 | 4200136290 | 251882480 | 95.4151 | 240333880 | -4.5849 |  |  | Job Completed | Deductional
31 |  | 190339/VHB | 4205622 | HDB Infront of WLC-WIN Workshop, Install Additional Shelter (Cat-2)_SMS #2nd | HCA | Actual | 11548600 | 4200138169 | 11548600 | 100 | 11548600 | 0 |  |  | Job Completed
32 |  | 190215/VHB | 4203990 | PLN Feeder for Handil Base Power Supply | HCA | Estimate | 461989390 | 4200132133 | 461989390 | 60.8568 | 281151911.1644 | -39.1432 |  |  | Job Completed | Deductional
33 |  | 190215/VHB | 4203990 | PLN Feeder for Handil Base Power Supply_SMS #2nd | HCA | Actual | 180837472.5717 | 4200138179 | 180837472.5717 | 100 | 180837472.5717 | 0 |  |  | Job Completed
34 |  | 190326/VHB | 4205596 | Overlay (Asphalting) of HDB Road | HCA | Estimate | 3980144384 | 4200132291 / Awaiting SMS INTERNAL | 3980144384.36 | 81.5318 | 3245083636.36 | -18.4682 | -735060748 |  | Hold
35 |  | 190289/VC | 4204954 | Relocation office, Clinic & Workshop | HCA | Estimate | 483266465 | 4200132759 | 483266465 | 94.6091 | 457213891 | -5.3909 |  |  | Job Completed | Deductional
36 |  | 190345/VH | 4205681 | WB_M1: Perform Site Trimming 2019 (1st) | HCA | Estimate | 388926725 | 4200132755 | 388926725 | 8.4655 | 32924570 | -91.5345 | -356002155 |  | Hold
37 |  | 190346/VH | 4205680 | WB_M2: Perform Site Trimming 2019 (1st) | HCA | Estimate | 247498825 | 4200132756 | 247498825 | 0 | 0 | -100 | -247498825 |  | Waiting Schedule
38 |  | 190347/VH | 4205679 | WB_M3: Perform Site Trimming 2019 (1st) | HCA | Estimate | 318212775 | 4200132757 | 318212775 | 0 | 0 | -100 | -318212775 |  | Waiting Schedule
39 | 14221833 | 190333/VH | 4205608 | Handil IV - Repair Control Box and Bundwall | HCA | Estimate | 239947250 | 4200133933 | 239947450 | [5 empty] | Job Completed
40 |  | 190215/VHB | 4209367 | PLN Feeder for Handil Base Power Supply (Cat-2) - Sub Item 190215-VHB,SMS #2nd | HCA | Estimate | 239714565 | 4200134015 | 239714565 | 96.79 | 232019727.4635 | -3.21 |  |  | Job Completed | Deductional
41 |  | SUB 19289/VC | 4211905 | CPA, Relocation office, clinic and workshop at CPA (Cat-2)_SMS #2nd | HCA | Estimate | 5530441072 | 4200135336 / Awaiting SMS INTERNAL | 5530441072 | [5 empty] | Job Completed
42 |  | 190255/VC | 4204477 - 2nd | Site Triming for INSP. Access, Gas Piping V6010 to TEG & X8990 Pilot #SMS 2nd | HCA | Estimate | 27698825 | 4200135931 | 27698825 | 100 | 27698825 | 0 |  |  | Job Completed
43 |  | 190285/VC | 4204886 | Site Survey, CPA Process, Replace All Utility and Fresh Water Distribution | HCA | Estimate | 53826825 | 4200136882 / 3700066074 | 53826825 | [5 empty] | Job Completed |  |  | Periode Juli
44 |  | 190817/VHB | 4212933 | HDB Handil Heliport, Digging for cable installation (Cat-2) | HCA | Estimate | 74692507 | 4200136400 | 60406205 | 59.6596 | 36038114 | -40.3404 |  |  | Job Completed | Deductional
45 |  | 180017/VH | 4188686 - 1st | HDB, Fasad improvement of cluster Tunu, Senipah, and Tambora (Cat-2)_SMS#1st | HCA | Estimate | 563454000 | 4200136884 | 563454000 | [5 empty] | Job Completed
46 |  | 180017/VH | 4188686 - 2nd | HDB, Fasad improvement of cluster Tunu, Senipah, and Tambora (Cat-2)_SMS#2nd | HCA | Estimate | 447374478.8 | 4200136885 / 3700066456 | 447374478.8 | [5 empty] | Job Completed |  |  | Periode Agustus
47 |  | 180017/VH | 4188686 - 3rd | HDB, Fasad improvement of cluster Tunu, Senipah, and Tambora (Cat-2)_SMS#3rd | HCA | Estimate | 720787909 | 4200136886 / 3700066180 | 720787908 |  |  | -100 | -720787908 |  | Onprogress |  |  | Periode Agustus, partial 1
48 |  |  | 4213661 | CPA camp, Build New HWTA CPA IN EX FOOTBALL FIELD | HCA | Estimate | 503848258 | 4200137217 | 503848258 | 98.3218 | 495392794.9935 | -1.6782 |  |  | Job Completed | Deductional
49 |  | 190788/HB | 4212448 | HDB, construct joging track at runway (cat-2) | HCA | Estimate | 91361628 | 4200136856 | 91361628 | 96.1674 | 87860112 | -3.8326 |  |  | Job Completed | Deductional
50 |  | 190788/HB | 4212448 | HDB, construct joging track at runway (cat-2)_SMS #2nd | HCA | Estimate | 3501516 | 4200138174 | 3501516 | 100 | 3501516 | 0 |  |  | Job Completed
51 |  | 190890/VH | 4214581 | HLB-176, Perform Site trimming (Cat-2) #SMS 2nd | HCA | Actual | 42399380 | 4200137303 | 42399380 | 100 | 42399380 | 0 |  |  | Job Completed
52 |  | 190905/VH | 4214764 | HC Gathering area, Performing cutting/removal trees d/t fallen to pipeline (Cat-2) | HCA | Actual | 7710895 | 4200136999 | 7710895 | 100 | 7710895 | 0 |  |  | Job Completed
53 |  | 190893/VH | 4214744 | HPA-313, Perform Site Trimming (Cat-2) | HCA | Estimate | 73013950 | 4200136996 | 73013950 | 67.2038 | 49068160 | -32.7962 |  |  | Job Completed | Deductional
54 |  | 180008/VHB | 4188292 - 2nd | HDB, repair shoreline helipad area (Cat-2) - SMS #2nd | HCA | Actual | 95708777.37 | 4200136607 | 95708777.37 | 100 | 95708777.37 | 0 |  |  | Job Completed
1 |  | 200192/VC | 4217937 | CPA Process, Repair Roof Control Room | CPA | Actual | 20179650 | 4200138537 | 20179650 | 100 | 20179650 | 0 |  |  | Job Completed
2 |  | 200317/VH | 4219351 | HN - CPA 6" Pipeline Site Clearing/Trimming on high vegetation for inspection access | CPA | Actual | 5439725 | 4200140469 | 5439725 | 100 | 5439725 | 0 |  |  | Job Completed
3 |  | 190921/VH | 4215021 | HL-273, Wellconn : Installa Chain Lingk (with material) for Fabrication Transformator Shelter. (Cat-2) | CPA | Estimate | 257851789 | 4200139546 | 244065992 | 100 | 244065992 | 0 |  |  | Job Completed
4 |  | 200153/VHB | 4217425 | HDB WAREHOUSE, Perform Improvement WHP Heavy Maintenance (Cat-2) | HCA | Estimate | 477774661 | 4200139867 | 477774661 | 67.0939 | 320557730 | -32.9061 |  |  | Job Completed | Deductional
5 |  | Sub | 4213661 - 2nd | CPA camp, Build New HWTA CPA IN EX FOOTBALL FIELD # SMS_2nd | CPA | Estimate | 68678474.4 | 4200140256 | 68678474.4 | 100 | 68678474.4 | 0 | 0 |  | Job Completed |  | 0
6 |  | 180141/VHB | 4189786 - 2nd | HDB, created shelter for CCU welding maintenance (Cat-2) - SMS #2nd | HCA | Actual | 107774760.58 | 4200140237 | 107774760.58 | 100 | 107774760.58 | 0 |  |  | Job Completed
7 |  | sub | 4220952 | HDB - CCU Shelter, Install Scaffolding for Assist CST / Electric Job (cat-2) | HCA | Actual | 30129100 | 4200140253 | 30129100 | 100 | 30129100 | 0 |  |  | Job Completed
8 |  | 200437 / VHB | 4220991 | HDB, Cleaning Hopper Barge LSM 11 (Cat-2) | HCA | Estimate | 339682225 | 4200140415 | 339682225 | 76.923 | 261293650 | -23.077 |  |  | Job Completed | Deductional
9 |  | 200342/VH | 4219717 | HK - M1 SEP, CPA 6" Pipeline Site Clearing/Trimming on high vegetation for inspection access | HCA | Actual | 48957525 | 4200140543 | 48957525 | 100 | 48957525 | 0 |  |  | Job Completed
10 |  | 200341/VH | 4219716 | HKA - HAB, CPA 6" Pipeline Site Clearing/Trimming on high vegetation for inspection access | HCA | Actual | 36577475 | 4200140470 | 36577475 | 100 | 36577475 | 0 |  |  | Job Completed
11 |  | 200340/VH | 4219715 | HVB - HZA, CPA 6" Pipeline Site Clearing/Trimming on high vegetation for inspection access | HCA | Actual | 40078875 | 4200140955 | 40078875 | 100 | 40078875 | 0 |  |  | Job Completed
12 |  | 200416/VH | 4220847 | HGB-475 Well Flow Line LS, Perform Site Trimming on High Vegetation for inspection Access | HCA | Estimate | 37717175 | 4200140609 | 37717175 | 100 | 37717175 | 0 |  |  | Job Completed
13 |  | sub | 4217425 - 2nd | HDB WAREHOUSE, Perform Improvement WHP Heavy Maintenance (Cat-2)_SMS #2nd | HCA | Actual | 33161252 | 4200141941 | 33161252 | 100 | 33161252 | 0 | 0 |  | Job Completed |  | 0
14 |  | 200493/VH | 7265548 | HH Burnt Pit Access way, Perfrom Site Trimming (Cat-1) | HCA | Actual | 14818575 | 4200140642 | 14818575 | 100 | 14818575 | 0 |  |  | Job Completed
15 |  | 200475/VH | 4221558 | HGB-W1, Perfom site trimming (Cat-2). | HCA | Estimate | 54079000 | 4200140570 | 54079000 | 97.9952 | 52994800 | -2.0048 |  |  | Job Completed | Deductional
16 | 17265549 | 200444/VH | 4221039 | HDL-IV Area Open/Close Drain, Perform Site Trimming d/t Hig Vegetation (CERMAT…) (Cat-2) | HCA | Estimate | 51521000 | 4200140650 | 51521000 | [5 empty] | Job Completed | Deductional
17 |  | 200474/VH | 4221536 | HGB Switchgear water well, Repair broken wall, ceiling and possible roof (Cat-2) | HCA | Estimate | 226563481.34 | 4200140935 | 226563481.34 | 92.8001 | 210251089 | -7.1999 |  |  | Job Completed | Deductional
18 |  | 200437 / VHB | 4220991 - 2nd | HDB, Cleaning Hopper Barge LSM 11 (Cat-2) - SMS #2nd | HCA | Actual | 12320200 | 4200141000 | 12320200 | 100 |  | 0 | 0 |  | Job Completed |  | 0
19 |  | sub 200475/VH | 4221558 - 2nd | HGB-W1, Perform site trimming - SMS Actual #2nd | HCA | Actual | 11518950 | 4200141304 | 11518950 | 100 | 11518950 | 0 | 0 |  | Job Completed |  | 0
20 |  | 200530/HBE | 4222211 | HDB, Construct Foundation, Fabrication & install lightning Pole (Cat-2) | HCA | Estimate | 350390161 | 4200141401 | 350390161 | [5 empty] | Job Completed partial |  |  | Partial FAC-1 (belum ada HOC)
21 |  | 200562/VH | 4222846 | M2, Perform Site clearing on high vegetation (Cat-2) | HCA | Actual | 18820175 | 4200141403 | 18820175 | 100 | 18820175 | 0 |  |  | Job Completed
22 |  | 200182/VH /200551/VH | 4217882 / 7266763 | HK-454 LS Well Flowline, Perform site clearing on high vegetation for inspection access (Cat-2) | HCA | Actual | 41079275 | 4200142010 | 41079275 | 100 | 41079275 | 0 |  |  | Job Completed
23 |  | 200568/VC | 4222976 | HGL Switchgear, Remove/reinstall Wall & Floor/frame for access Welding Hole MCT Cable of New HVAC (Cat-1) - Sub WO item 200553/C | HCA | Actual | 13424900 | 4200141404 / 3700066736 | 13424900 | 100 | 13424900 | 0 | 0 |  | Job Completed |  | 0 | belum ada sms actual approval
24 |  | 200488/VC | 4221692 | Gascomp LP-1 Compressor Tech' Room, Broken Roof Repair (Cat-1) | HCA | Estimate | 109330720 | 4200141417 | 109330720 |  |  | -16.03 | -17525714.416 |  | Job Completed
25 | 14239124 | 200491/VC | 4221750 | Gascomp HP-2 Gas Turbo Commpressor, Tech' Room Roof Repair (Cat-1) | HCA | Estimate | 130008820 | 4200141878 | 130008820 |  |  | -56.45 | -73389978.89 |  | Job Completed
26 |  | 200483/VC | 4221650 | BSB/AEB Batery Room, Broken Roof & Cilling Repair (Cat-1) | HCA | Estimate | 147356500 | 4200142006 | 147356500 |  |  | -16.6825 | -24582820.8 |  | Job Completed
27 |  | 200498/C | 4221881 | CPA New Office A & B, Provide Horizontal Blind (Cat-1) | HCA | Actual | 52174086 | 4200141418 | 52174086 | 100 | 52174086 | 0 | 0 |  | Job Completed |  | 0
28 |  | 200092/VHB | 4216521 | HDB Bravo-1, Revamping supervisor office (Cat-2) | HCA | Estimate | 249007596 | 4200141514 / Awaiting INFO | 249007596 |  |  | -100 | -249007596 |  | Waiting info
29 |  | 200571/VH | 4223026 | HA-M2 12" pipeline, Perform Site Trimming ILI facilities at HA & M2 (Cat-2) | HCA | Actual | 12380050 | 4200141441 | 12380050 | 100 | 12380050 | 0 |  |  | Job Completed
30 |  | 200569/VC | 4222951 | CPA Office A, Construct Land Reinstatement (Cat-1) | HCA | Actual | 59042200 | 4200141850 |  | 100 |  | 0 |  |  | Job Completed
31 |  | 200476/VH | 7265133 | HGD cluster gas volume bottle, Perform site clearing on high vegetation for inspection access (CeRMAT xxxx) (Cat-2) | HCA | Actual | 18820175 | 4200141942 | 18820175 | 100 | 18820175 | 0 | 0 |  | Job Completed |  | 0 | Info CST sudah ditagihkan full (18.8.2021) Ast Plan
32 |  | 200599/VC | 4223388 | CPA, Construct temporary fence at ex-office and ex-workshop (Cat-1) | HCA | Actual | 37037457 | 4200141958 | 37037457 | 100 | 37037457 | 0 | 0 |  | Job Completed |  | 0
33 |  | 200216/VH | 7260027 | HK-556 SS, Perform Site Clearing (Cat-2) | HCA | Estimate | 38640750 | 4200142016 |  |  |  |  | -38640750 |  | Waiting info
34 | 17269182 | 200608/VH | 4223504 | HTC, Perform site trimming (Cat-2) | HCA | Actual | 59399250 | 4200142108 | 5439725 | [5 empty] | Job Completed
35 |  | 200614/VC | 4223544 | BSB/AEB TR-8401, Broken Roof Repair (Cat-1) | HCA | Actual | 80775975 | 4200142109 | [6 empty] | Job Completed
36 | 17262094 | 200300/VH | 7261453 | HZC-HKA gathering, Perform site clearing (Cat-2) | HCA | Actual |  | 4200142060 1st) - 42001429942 (2nd) | 100916250 | [5 empty] | Job Completed
37 |  | 200570/VHB | 4222912 | HDB pipe yard area, Replace corroded barbed wire of fence at pipe yard (Cat-2) | HCA | Estimate | 284235401 | 4200141879 / Awaiting NEW CRO | 284235401 | [5 empty] | Job Completed |  |  | partial pertama 80.222.780 periode maret
38 |  | 200677/VC | 4224209 | HGL Switchgear, Repair HGL Switchgear roof (Cat-1) | HCA | Actual | 11892713 | 4200142708 | 11892713 | 100 | 11892713 |  |  |  | Job Completed
39 | 17265488 | 200441/VH | 4221009 | HGD-462 & HGD-464, Perform Site Clearing / Trimming on High Vegetation for inspection access on HGD MDF (Cat -2) | HCA | Actual | 42976450 | 4200142712 | 30199825 | [5 empty] | Job Completed
1 | 14231777 | 200056/VH | 4215747 | HOA Walkway, Perform clearing vegetation for KEHATI program | HCA |  | 108794500 | 4200143070 | [6 empty] | Job Completed
2 | 14241948 | 200642/VHB | 4224082 | Assist GNS to install scaffolding at cluster bekapai | HCA | Actual | 15943250 | 4200142713 | 15943250 | [5 empty] | Job Completed
3 | 17263119 | 200344/VH | 4219719 | HGD, HK Gathering Line Support, Perform Site Clearing (Cat-2) | HCA | Actual | 128802500 | 4200142598 | 54959925 | [5 empty] | Job Completed |  |  | Info CST sudah ditagihkan full (18.8.2021) Ast Plan
4 | 17265551 | 200445/VH | 4221038 | HY Cluster W/Way to Pit Area, Perform Site Trimming d/t Covered High Vegetation (CeRMAT….) (Cat-2) | HCA | Actual | 85425535 | 4200143364 | [5 empty] | PRD | Job Completed
5 | 14243420 | 210096/VC | 4225298 | CPA, Modify roof structure of CPA Control Room | HCA | Actual |  | 4200143362 | 12204300 |  |  |  |  | PRD | Job Completed
6 | 14241669 | 200634/VB | 4223868 | HDB, Replace broken sirap roof to metal roof - SMS #1st | HCA | Estimate | 491236707 | 4200143612 / 3700066457 | [5 empty] | GNS | Job Completed |  |  | Periode Agustus
7 | 14242250 | 210002/VHB | 4224348 | HDB Pipe Yard. Repair the broken ditch and ditch system _Zone A - SMS #1st | HCA | Estimate | 797738550 | 4200143798 / 3700066181 | [5 empty] | LSA | Onprogress |  |  | Periode Agustus, partial ke 1
8 | 14232065 | 200066/VC | 4216076 | CPA Near Camp (Cluster-C) to HOA, Walk Way Repair (Cat-1) -SMS #1st | HCA | Estimate | [8 empty] | Waiting info
9 | 14222505 | 190462/VH | 4207186 | HDL-IV, Repair broken support of fence (CeRMAT 565869) (Cat-2) | HCA | Estimate | 109380720 | 4200144359 / Awaiting INFO | [6 empty] | Waiting info |  |  | CRO Baru dibuat setelah ada progress
10 | 17247321 | 190428/VH | 7246456 | HDL-IV, Repair broken fence (CeRMAT 561742) (Cat-2) | HCA | Estimate | 80176656 | 4200144313 / 3700066075 | [6 empty] | Job Completed |  |  | Periode Juli
11 | 19029700 | 210124/H | 4225466 | HLA-HLB ROW area, Performing cutting/clearing trees from pipeline on the pipe rack | HCA | Actual | 7378050 | 4200143365 | [6 empty] | Job Completed
12 | Sub | 210185/VHB | 4225907 | HDB, Foundation Guyed Wire | HCA | Estimate | 177095415 | 4200143609 | [6 empty] | Job Completed
13 | 14244229 | 210193/VH | 4225965 | HGC, Perform Site Trimming | HCA | Actual | 96601875 | 4200143871 | [5 empty] | PRD | Job Completed
14 | 14242250 | 210002/VHB | 4224348 - 2nd | HDB Pipe Yard. Repair the broken ditch and ditch system _Zone B - SMS #2nd | HCA | Estimate | 471145614 | 4200144414 / 3700066742 | [5 empty] | LSA | Onprogress
15 | 14242250 | 210002/VHB | 4224348 - 3rd | HDB Pipe Yard. Repair the broken ditch and ditch system _Zone C - SMS #3rd | HCA | Estimate | 583810861 | 4200144415 / 3700066749 | [5 empty] | LSA | Onprogress
16 | sub | 180017/VHB | 4225982 - 4th | Sub 180017/thVHB Fasad Improvement of cluster - SMS #4th | HCA | Estimate | 158637548 | [6 empty] | GNS | canceled
17 | sub | 210192/VH | 4225948 | HGB-HGC, Site Trimming Pipeline area for access repair pipe support (Related 180606H) | HCA | Estimate | 15318775 | 4200143670 | [5 empty] | PRD | Job Completed
18 | 14244116 | 210184/VHB | 4225834 | HDB, Cleaning sediment at Hoper Barge LSM -10 | HCA | Estimate | 307976950 | 4200143689 | [6 empty] | Job Completed
19 | 14221833 | 190333/VH | 4205608 - 2nd | Handil IV - Repair Control Box and Bundwall - SMS #2nd | HCA | Actual | 23195622 | 4200143363 | [5 empty] | PRD | Job Completed
20 |  | 210219/VH | 7272067 | HQ Pit Line, Perform Site Trimming | HCA | Actual | 6440125 | 4200143701 | [5 empty] | PRD | Job Completed
21 | 17273576 | 210200/VC | 7271811 | Repair top roof/deck at ceiling of CPA control room | HCA | Actual | 7784000 | 4200143880 | [5 empty] | PRD | Job Completed
22 | 17274211 | 210236/VH | 4226400 | HFA - HTC, Perform site clearing/trimming on high vegetation for inspection access | HCA | Actual | 71279100 | 4200144346 / 3700066076 | [5 empty] | INS | Job Completed |  |  | Periode Juli
23 | sub | 210226/VHB | 7272212 | HDB, Pouring concrete around FW line related to job item 200389/HB | HCA | Actual | 5719900 | 4200143881 | [5 empty] | SE | Job Completed
24 | 14245006 | 210247/VHB | 4226526 | HN - HW, Perform site trimming d/t high vegetation to identify pipe line condition | HCA | Actual | 96601875 | 4200144068 / 3700066455 | 42029850 |  |  |  |  | PRD | Job Completed |  |  | Periode Juli
25 | 14229067 | 190827/VH | 4213148 | HN - HW, Remove Fallign die tress d/t push to pipe line support getting broken | HCA | Actual | 17757300 | 4200144070 / 3700066109 | 7865600 |  |  |  |  | INS | Job Completed |  |  | Periode Juli
26 | 14245186 | 210251/VC | 4226646 | Miscelllaneous work at CPA | HCA | Estimate | 158637548 | 4200143608 / 3700066183 | [5 empty] | GNS | Hold |  |  | Periode Agustus, partial ke 1
27 | 14245420 | 210262/VH | 4226822 | HW - HL, Perform site trimming d/t high vegetation to identify pipeline | HCA | Actual | 45080875 | 4200144195 / 3700066077 | [5 empty] | PRD | Job Completed |  |  | Periode Juli
28 | 14242250 | 210002/VHB | 4224348 - 4th | HDB Pipe Yard. Repair the broken ditch and ditch system _ZoneD - SMS #4th | HCA | Estimate | 446412641.4 | 4200144517 / 3700066782 | [5 empty] | LSA | Onprogress
29 | 14242250 | 210002/VHB | 4224348 - 5th | HDB Pipe Yard. Repair the broken ditch and ditch system _ZoneE - SMS #5th | HCA | Estimate | 514705462.9 | 4200144519 / 3700066801 | [5 empty] | LSA | Onprogress
30 | 14242250 | 210002/VHB | 4224348 - 6th | HDB Pipe Yard. Repair the broken ditch and ditch system _ZoneF - SMS #6th | HCA | Estimate | 227687175.56 | 4200144549 / 3700066095 | [5 empty] | LSA | Hold |  |  | Partial 1 juli & Partial 2 agustus
31 | 14242250 | 210002/VHB | 4224348 - 7th | HDB Pipe Yard. Repair the broken ditch and ditch system _ZoneG- SMS #7th | HCA | Estimate | 468019577.56 | 4200144553 / 3700066805 | [5 empty] | LSA | Onprogress
32 | 14241669 | 200634/VB | 4223868 - 2nd | HDB, Replace broken sirap roof to metal roof - SMS #2nd | HCA | Estimate | 787009623 | 4200143998 /3700066185 | [5 empty] | GNS | Hold |  |  | Periode Agustus, partial ke 1
33 | 17229122 | 180341/VH | 4193363 | HFA to Burn pit, Perform site clearing on high vegetation for inspection access | HCA | Actual | 45080875 | 4200144305 / 3700066096 | [5 empty] | INS | Job Completed |  |  | Periode Juli
34 | 17274907 | 210269/VHB | 4226931 | Assist scafolding at Social Room | HCA | Actual | 10460825 | 4200144261 / 3700066104 | [5 empty] | GNS | Job Completed |  |  | Periode Juli
35 |  | 210186/VHB | 4225908 | Install LPS and additional new Foundation | HCA | Actual | 227460565 | Awaiting NEW CRO | [5 empty] | GNS | Job Completed
36 | 17273760 | 210218/VH | 7272018 | HA, Perform site trimming on walkway to pit area | HCA | Actual | 64401250 | 4200144347 / 3700066108 | [6 empty] | Job Completed |  |  | Periode Juli
37 | 17274045 | 210231/VC | 4226290 | Repair Bundwall of HCA transient Pit | HCA | Actual | 85414950 | 3700066211 | [6 empty] | Job Completed |  |  | Periode Agustus
38 | 14246143 | 210315/VC | 4227417 | Repair Floor above HGL Switchgear (HVAC-2) | HCA | Actual | 78752175 | 4200144493 /3700066059 | [6 empty] | Job Completed |  |  | Periode Juli
39 |  | 200483/VC | 4221650 - 2nd | BSB/AEB Batery Room, Broken Roof & Cilling Repair (Cat-1) - SMS #2nd | HCA | Actual | 9909923 | 4200144492 / 3700066060 | [6 empty] | Job Completed |  |  | Periode Juli
40 | 14246361 | 210327/VHB | 4227542 | Sediment cleaning up of drainage along PHM fence | HCA | Estimate | 85778350 | 4200144750 / 3700066658 | [5 empty] | SVP/SWA | Job Completed
41 | 14242680 | 210039/VH | 4224696 | Perform site clearing on HS - Line from PSV & Relief to Pit for access inspection' | HCA | Actual | 59399250 | 3700066212 | [5 empty] | INS | Job Completed |  |  | Periode Agustus
42 | 14246260 | 210318/VH | 4227476 | Perform trimming of trees at HS cluster due to lot of caterpillars | HCA | Actual | 59399250 | 3700066217 | [5 empty] | INS | Job Completed |  |  | Periode Agustus
43 | 14246443 | 21330/VC | 4227601 | Reinforce building of new Controll Room (ex. Clinic) | HCA | Estimate | 206703878 | Awaiting NEW CRO | [6 empty] | Onprogress
44 | 17259132 | 200140/VC | 7258712 | Perform site trimming on walkway M3 pit from jetty area | HCA | Estimate | 45080875 | 4200144751 / 3700066187 | [5 empty] | HCA/PRD | Job Completed |  |  | Periode Agustus
45 |  | 180017/VH | 4188686 - 2nd - Phase 2 | HDB, Fasad improvement of cluster Tunu, Senipah, and Tambora (Cat-2)_SMS#2nd - Phase 2 | HCA | Estimate | 170171167 | RFA 3700066816 | [5 empty] | SVP/SWA | Job Completed
46 | 14247223 | 210362/VH | 4228201 | HNA-113/107, Site Trimming for access pipeline installation (WBS Wellconnection) | HCA | Actual | 7878250 | Awaiting NEW CRO | [5 empty] | HCA/INS | Job Completed
47 | 14233359 | 200139/VC | 4217251 | Perbaikan Walk-way ke arah CPA-Tower | HCA | Estimate | 145198830 | Awaiting INFO | [5 empty] | HCA/INS | Waiting info |  |  | CRO Baru dibuat setelah ada progress
48 | 14300129 | 210378/VHB | 4300260 | Cleaning Hopper Barge LSM12 | HCA | Estimate | 297830050 | RFA 3700066817 | [6 empty] | Job Completed
49 | 14241669 | 200634/VB | 4223868 - 3rd | HDB, Replace broken sirap roof to metal roof - SMS #3rd | HCA | Estimate | 712416767 | Awaiting INFO | [6 empty] | Waiting info |  |  | CRO Baru dibuatkan setelah ada progress
50 |  | 180017/VH | 4188686 - 5rd | HDB, Fasad improvement of cluster Tunu, Senipah, and Tambora (Cat-2)_SMS#5th | HCA | Estimate | 370612860 | Awaiting INFO | [6 empty] | Waiting info |  |  | CRO Baru dibuatkan setelah ada progress
51 |  | 210380/VH | 4300398 | HNA-107, Provide sandbags 400ea for RIG YANI | HCA | Actual | 38663000 | RFA 3700066652 | [6 empty] | Job Completed
52 | 14300493 | 210397/VH | 4300550 | HN Cluster, Perform Site Trimming - SMS #1st | HCA | Actual | 3939125 | RFA 3700066669 | [6 empty] | Job Completed
53 | 14300493 | 210397/VH | 4300550 - 2nd | HN Cluster, Perform Cutting trees - SMS #2nd | HCA | Actual | 81461875 | RFA 3700067608 | [6 empty] | Job Completed
54 | 14300494 | 210398/VH | 210398/VH | HEA-334 Site Preparation, Site Trimming Dredging Limit | HCA | Actual | 4945850 | Awaiting NEW CRO | [6 empty] | Job Completed
55 |  | 210186/VHB | 4225908 - Phase 2 | HDB, Install LPS (additional Foundation) - HCA Area | HCA | Internal SMS | 101294898 | Awaiting NEW CRO | [6 empty] | Job Completed
56 | 14301224 | 210448/VH | 4301260 | HNA-113/107 Wellcon, Assist piping prepare access at HN Burn pit for 8" Relief line | HCA | Actual | 16988775 | RFA 3700068180 | [6 empty] | Job Completed
57 | 14247223 | 210362/VH | 4228201 - 2nd | HNA-113/107, Cutting trees for access pipeline installation (WBS Wellconnection) - SMS #2nd | HCA | Actual | 5078825 | RFA 3700068120 | [6 empty] | Job Completed
58 | 14300493 | 210397/VH | 4300550 - 3rd | HN Cluster, Perform cleaning area after cutting trees - SMS #3rd | HCA | Actual | 5119025 | RFA 3700068119 | [6 empty] | Job Completed
CPU 2019,2020 & 2021
1 |  |  | 4192340 | New Extention of Fence at Flyway Area | CPU | Estimate | 826847290 | 4200131849 | 826847290 | 90.002 | 744179425.5 | -9.998 | -82667864.5 |  | Job Completed | Deductional
2 |  | 18C153C | 4194286 | Camp - Restaurant Revamping (Floor Tile Replacement at Dishwashing and Preparation Room) | CPU | Estimate | 103941450 | 4200132012 | 103941450 | 94.4444 | 98166925 | -5.5556 | -5774525 |  | Job Completed | Deductional
3 |  |  | 4204433 | Camp, Construct New Walkway from Clinic to KAHATI Area | CPU | Estimate | 48325815 | 4200131767 | 61412800 | 100 | 61412800 | 0 | 0 |  | Job Completed
4 |  |  | 5004560 | Tambora - Site Clearing at TM 132/136 for Site Preparation Well Conn | CPU | Estimate | 49185700 | 4200131627 | 44455730 | 100 | 44455730 | 0 | 0 |  | Job Completed
5 |  | 19CC99/CC | 4205184 | Camp - Walkway Access KEHATI | CPU | Estimate | 839361933 | 4200132041 | 839361933 | 100 | 839361933 | 0 | 0 |  | Job Completed
6 |  |  | 4209283 | Site Trimming TM-31 For Site Preparation | CPU | Estimate | 72851280 | 4200134039 | 72851280 | 53.7098 | 39128300 | -46.2902 | -33722980 |  | Job Completed | Deductional
7 |  |  | 7247030 | Camp, Replace Disposal Water pipe Near Restourant | CPU | Estimate | 119865490 | 4200133966 | 119865490 | 100 | 119865490 | 0 | 0 |  | Job Completed
8 |  |  | 4209001 | TM-43, Repair Pipeline Clamp (Civil Scope) | CPU | Estimate | 129742640 | 4200134523 | 129742637 | 100 | 129742637 | 0 | 0 |  | Job Completed
9 |  | 19C228/CC | 4211719 | Repair Weather Station | CPU | Estimate | 6650871.3 | 4200135297 | 6650871.3 | 100 | 6650871.3 | 0 | 0 |  | Job Completed
10 |  | 19T216/CC | 7252221 | Site Trimming Walkway Access GTS-2X to GTS-2 | CPU | Estimate | 25322780 | 4200135167 | 25322780 | 100 | 25322780 | 0 | 0 |  | Job Completed
11 |  |  | 4204791 | Installation Pipe 4" HDPE for Portable Water | CPU | Estimate | 259941040 | 4200133584 | 259941040 | 49.1452 | 127748531 | -50.8548 | -132192509 |  | Job Completed | Deductional
12 |  |  | 4210752 | Site Trimming Flare Area at TRF | CPU | Estimate | 61324730 | 4200135278 | 61324730 | 100 | 61324730 | 0 | 0 |  | Job Completed
13 |  |  | 4212336 | Site Trimming Sorrounding pipeline TM-31_RC35 for well connect | CPU | Estimate | 95017500 | 4200135784 | 95017500 | 100 | 95017500 | 0 | 0 |  | Job Completed
14 |  | 19C274/CC | 4213681 | Camp, Restaurant Kitchen Salad Room Tile Replacement | CPU | Estimate | 17323580 | 4200136243 | 17323580 | 100 | 17323580 | 0 | 0 |  | Job Completed
15 |  | 19C177/CC | 4212207 | Wooden Stage for construct new gutter and lisplank at CPU Accomodation building | CPU | Estimate | 16511198.76 | 4200136147 | 16511198.76 | 100 | 16511198.76 | 0 | 0 |  | Job Completed
16 |  |  | 4213807 | Camp, Assist Install Kehati Door | CPU | Estimate | 21495545 | 4200136409 | 21495545 | 100 | 21495545 | 0 | 0 |  | Job Completed
17 |  | 19C305/CC | 4214749 | Camp - Construct Walkwat at Runway (Security Post ke Hati) | CPU | Estimate | 105095557 | 4200136964 | 105095557 | 100 | 105095557 | 0 | 0 |  | Job Completed
18 |  |  | 4209096 | Construct New Gutter and Listplank at Accomodation Building at CPU | CPU | Estimate | 673766711.7638 | 4200135286 | 673766711.76 | 100 | 673766711.76 | 0 | 0 |  | Job Completed
19 |  |  | 4213969 | Repair Shoreline Cluster K (Temporary) | CPU | Estimate | 229031025 | 4200136466 | 229031025 | 100 | 229031025 | 0 | 0 |  | Job Completed
1 |  | 20C001/CC | 4215283 | Repair lisplank PJC - Camp Library building | CPU | Estimate | 30828000 | 4200137421 | 30828000 | 100 | 30828000 | 0 |  |  | Job Completed
2 |  | 20C084/CC | 4218140 | CAMP - Revamping HWTA for Proper Visit | CPU | Estimate | 132399560 | 4200139279 | 132399560 | 35 |  | -65 |  |  | Job Completed
3 |  | 20C113/CC | 4219621 | Temporary Repair Land Slide Shorline Near Toilet Cluster K | CPU | Estimate | 263488400 | 4200139701 | 263488400 | 100 | 263488400 | 0 |  |  | Job Completed
4 |  | 20C130/CC | 4220315 | Install New Halipad Lamp | CPU | Estimate | 24044900 | 4200139966 | 24044900 | 100 | 24044900 | 0 |  |  | Job Completed
5 |  | 20C117/CC | 4219918 | CAMP PASSANGER JETTY CONCRETTE ROBUST MARKER OF MARINE HAZARD | CPU | Estimate | 4217780 | 4200139679 | 4217780 | 100 | 4217780 | 0 |  |  | Job Completed
6 |  | 0 | 4221699 | Tambora - Site Trimming to install Jumper Line at TM-92 (Civil Scope Well Conn TM-137 | CPU | Estimate | 24313200 | 4200140735 | 24313200 | 100 | 24313200 | 0 |  |  | Job Completed
|  | 0 | 7258636 | Repair Wall of Crossing Ditch at Flyway Area | CPU | Estimate | 590246418 | 4200141277 | 590246418 | [5 empty] | Job Completed
|  | 20C266/CC | 4221874 | CAMP - CHURCH SITE TRIMMING | CPU | Estimate | 6446450 | 4200140920 | 6446450 | 96.12 | 6196325 | -3.88 |  |  | Job Completed | Deductional
|  | 20T271/CC | - | Site Trimming on shore at surrounding TM-34 for dredging | CPU | Actual | 5946200 | 4200141151 | 5946200 | 100 | 5946200 | 0 |  |  | Job Completed
|  | 0 | 4211718 | Repairing Shoreline Protection near by loading jetty area | CPU | Estimate |  | 4200139704 | 467423220 | [5 empty] | Job Completed
|  | 0 | 4221973 | SITE TRIMMING RC#08 GOV-4802 | CPU | Estimate | 14865625 | 4200141276 | 14865625 |  | 9947850 |  |  |  | Job Completed |  |  | Revisi BOQ (dokumen approval baru diterima juli 2021) penyesuaian dokumen
1 | 14241743 |  | 4223910 | CONSTRUCT WOODEN BOX FOR LO COOLER TEG 9610 | CPU | Actual | 7868747 | 4200142395 | [6 empty] | Job Completed
2 | 14242453 |  | 4224471 | Tambora - TM32 Site Trimming for Site Preparation (Well Con) | CPU | Estimate | 46215875 | 4200142664 | [6 empty] | Job Completed
3 | 17268845 |  | 7267331 | CAMP - REPAIR SIRING & FENCE NEAR CLUSTER K TO SECURITY POST | CPU | Estimate | 304434772 | 4200141623 | [6 empty] | Job Completed
4 | 17272156 |  | 7270368 | PERBAIKAN SALURAN AIR JOGGING TRACK | CPU | Estimate | 30995919.9967 | [7 empty] | Job Completed
5 | 14242043 |  | 4224186 | CUTTING TREE AT RC-15 | CPU | Estimate | 37974350 | [7 empty] | Waiting info
6 | 14244132 |  | 4225863 | Perform, site clearing at P/S 36" TMP 2 - STP 3 | CPU | Actual | 1000400 | 4200143406 | [6 empty] | Job Completed
7 |  |  | 7271763 | TRF - REPAIR LANDSLIDE AT ENTRANCE OF JETTY KUTAI LAMA | CPU | Actual | 6418375 | 4200143884 | [6 empty] | Job Completed
8 | 14240490 |  | 4222893 | CAMP - CONSTRUCT ACCESS WALKWAY TO SMOKING CORNER CPU ANPOL | CPU | Estimate | 28345905 | 4200141406 | [6 empty] | Job Completed |  |  | Done HOC 3.7.21
9 | 17275280 |  | 7273577 | CAMP - REPAIR JOGGING TRACK AT NEAR MAIN GATE SECURITY POST | CPU | Estimate | 40662400 | 4200144329 / 3700066835 | 40662400 | [5 empty] | Job Completed
10 |  |  | 4226546 | Camp - Perform site trimming near Heliport | CPU | Actual | 42161400 | 4200144379 / 3700066834 | 42161400 | [5 empty] | Job Completed
11 |  |  | 4226848 | Perform site trimming at walkway | CPU | Actual | 14921775 | [7 empty] | Job Completed
12 |  |  | 7273771 | Excavation for repair leakage pipe PWAT | CPU | Actual | 44730875 | 4200144394 / 3700066863 | [6 empty] | Job Completed
13 | 1726805 |  | 7266665 | CAMP - Memeperbaiki atap keropos di PJC Camp | CPU | Estimate | 178891258 | 4200142635 / 3700065935 | 178891258 | [5 empty] | Job Completed
14 |  |  | 7274471 | CAMP - EXCAVATION FOR REPAIR LEAKAGE PIPE PWAT | CPU | Estimate | 58204375 | 4200144614 / 3700066869 | 58204375 | [5 empty] | Job Completed
15 | 14241641 |  | 4223933 | Site Trimming at Walkway RC-14 | CPU | Actual | 4473725 | 3700066872 | [6 empty] | Job Completed |  |  | Start & done 26.06.21
16 |  |  | 4225491 | Camp - Radio Shelter CPU Repair 2nd Floor, Wall & Ceiling (SYN #575747) - CPU Area | CPU | Estimate | 755362740 | [7 empty] | Onprogress
17 |  |  | 4226848 - 2nd | TM 114/93/117 - Perform Site Trimming At Walkway (SYN - 576602) | CPU | Estimate | 2000800 | [7 empty] | Waiting info
18 |  |  | 4223247 | RC 12 - Perform Site Trimming (SYN #574496) | CPU | Estimate | 2472925 | 3700066870 | [6 empty] | Job Completed
19 |  |  | 7270368 | PERBAIKAN SALURAN AIR JOGGING TRACK - SMS #2nd | CPU | Estimate | 61967876 | [7 empty] | Job Completed |  |  | Deduction
20 | 17258868 | 20C084/CC | 4217158 | CAMP - PERBAIKAN TALANG DAN LISPLANK RESTO CPU | CPU | Estimate | 315501730 | [7 empty] | Waiting info
21 |  |  | 4226736 | Camp Perform Site Trimming At Fence Accomodation (ANM-210407) | CPU | Actual | 14921775 | 4200144308 / 3700066833 | [6 empty] | Job Completed |  |  | Pekerjaan Selesai, Belum dijual (sudah ditagihkan periode agustus
SPU 2019,2020 & 2021
1 |  |  | 4188984 | Roof Extention on Mosque Area | SPU | Estimate | 133377988 | 4200132351 | 133377988 | 92.9313 | 123949933 | -7.0687 |  |  | Job Completed | Deductional
2 |  |  | 4202921 | New Gate Access to KEHATI Area | SPU | Estimate | 31848179 | 4200132508 | 31848179 | 100 | 31848179 | 0 |  |  | Job Completed
3 |  | 19P706/SC | 4197278 | Perform Site Trimming along SUP - SMP | SPU | Estimate | 150929100 | 4200131288 | 150929100 | 90.4762 | 136554900 | -9.5238 |  |  | Job Completed | Deductional
4 |  |  | 4197605 | SNPS Site Clearing on ESDV P/F (GOV Area) | SPU | Estimate | 13373800 | 4200131443 | 13373800 | 100 | 13373800 | 0 |  |  | Job Completed
5 |  |  | 4201762 | TMP-1 Site Clearing at Emergency Pit | SPU | Estimate | 13373800 | 4200131444 | 13373800 | 100 | 13373800 | 0 |  |  | Job Completed
6 |  |  | 4201766 | GTS-R Site Clearing at Emergency Pit | SPU | Estimate | 20060700 | 4200131445 | 20060700 | 100 | 20060700 | 0 |  |  | Job Completed
7 |  |  | 4203511 | Install Wooden skid for slug catcher train A and B | SPU | Estimate | 81880059.92 | 4200131287 | 100236859 | 43.6538 | 43757167 | -56.3462 |  |  | Job Completed | Deductional
8 |  |  | 4198550 | SPU Camp - © Site Clearing at Jetty Riyani | SPU | Estimate | 13373800 | 4200131442 | 13373800 | 100 | 13373800 | 0 |  |  | Job Completed
9 |  |  | 4193613 | Site Trimming Around Walk Way and Between Platform Adjacent Well GTS-H | SPU | Estimate | 21561300 | 4200131502 | 21561300 | 100 | 21561300 | 0 |  |  | Job Completed
10 |  |  | 4192086 | Site Trimming at Walkway TN-W12/R50 Area as per Cermat | SPU | Estimate | 13373800 | 4200131446 | 13373800 | 100 | 13373800 | 0 |  |  | Job Completed
11 |  |  | 4209369 | SPU Canopy Passangger Jetty | SPU | Estimate | 216609838 | 4200134099 | 216609838 | 100 | 216609838 | 0 |  |  | Job Completed
12 |  |  | 4193117 | GTS-J Site Trimming Around/Vegetation Emergency Pit | SPU | Estimate | 26747600 | 4200131945 | 26747600 | 100 | 26747600 | 0 |  |  | Job Completed
13 |  |  | 4201690 | Repair Bundwall Flare Pit GTS-F | SPU | Estimate | 81880059.92 | 4200131747 | 42766172 | 100 | 42766172 | 0 |  |  | Job Completed
14 |  |  | 4198568 | Construct Shelter for CGC | SPU | Estimate | 134030098 | 4200132420 | 134030098 | 100 | 134030098 | 0 |  |  | Job Completed
15 |  |  | 4204625 | SPU Site Trimming Around Camp Perimeter | SPU | Estimate | 26747600 | 4200131944 | 25747200 | 100 | 25747200 | 0 |  |  | Job Completed
16 |  |  | 4205114 | Repair Bundwall Emergency Pit GTS-E | SPU | Estimate | 83784536 | 4200132381 | 83784536 | 100 | 83784536 | 0 |  |  | Job Completed
17 |  |  | 4205883 | Perform Site Trimming to Open Access from GTS-F Emergency Pit to GTS-FX | SPU | Estimate | 21561300 | 4200132439 | 21561300 | 57.3871 | 12373400 | -42.6129 |  |  | Job Completed | Deductional
18 |  |  | 4205861 | Repair Bundwall Emergency Pit GTS-J | SPU | Estimate | 57062790 | 4200132441 | 57062790 | 100 | 57062790 | 0 |  |  | Job Completed
19 |  |  | 4205113 | Repair Bundwall Emergency Pit GTS-G | SPU | Estimate | 97480518.63 | 4200132440 | 97480518.63 | 98.3541 | 95876065.03 | -1.6459 |  |  | Job Completed | Deductional
20 |  |  | 7248171 | Performe Site Trimming at Accessway SNPS to ECB | SPU | Estimate | 21561300 | 4200133691 | 21561300 | 100 | 21561300 | 0 |  |  | Job Completed
21 |  |  | 4208065 | Perform Site Trimming at MP2 Area | SPU | Estimate | 35935500 | 4200133692 | 35935500 | 60 | 21561300 | -40 |  |  | Job Completed | Deductional
22 |  |  | 4206437 | GTS FX - Site Trimming Adjacent Well Walk Way | SPU | Estimate | 28748400 | 4200133745 | 28748400 | 75 | 21561300 | -25 |  |  | Job Completed | Deductional
23 |  |  | 4208808 | Site Trimming Cold Vent GTS-AC | SPU | Estimate | 50309700 | 4200134037 | 50309700 | 71.4286 | 35935500 | -28.5714 |  |  | Job Completed | Deductional
24 |  |  | 195397 | Trees Inventory for Site Preparation TN-69/70/71, Inc Site Trimming Tree's under 10 cm for Access | SPU | Estimate | 173448421.67 | 4200134754 | 173448421.67 | 100 | 173448421.67 | 0 |  |  | Job Completed
25 |  |  | 195398 | Site Trimming at TN-R 69/70/71 for Site Praparation | SPU | Estimate | 284990534.4 | 4200134756 | 284990534.4 | 100 | 284990534.4 | 0 |  |  | Job Completed
26 |  |  | 4210472 | Camp : Re-Trimming FATO 020 Heliport | SPU | Estimate | 271886312.5 | 4200134598 | 271886312.5 | 100 | 271886312.5 | 0 |  |  | Job Completed
27 |  | 17T456/S | Sub 4180615 | Temporary Water Line and Facility for Potable Water Tank | SPU | Estimate | 160742423 | 4200135588 | 160742423 | 98.5231 | 158368362 | -1.4769 |  |  | Job Completed | Deductional
28 |  |  | Sub4180615 | Additional Temporary Water Line and Facility for PWT (#SMS-3) | SPU | Estimate | 17980200 | 4200136358 | 25270300 | 100 |  | 0 |  |  | Job Completed |  |  | Note: Revisi actualcost dari invoicing
29 |  | 190590/SC | 4212294 | Site Preparation RMI - Tasha install terpaulin around diesel | SPU | Estimate | 257482400 | 4200136092 | 228167600 | 100 | 228167600 | 0 |  |  | Job Completed
30 |  | 19T648/SC | 19T648/SC | Tree Inventory and Site Clearing TN-FX476 for Site Preparation | SPU | Estimate | 74677400 | 4200136944 | 74677400 | 95.9811 | 71676200 | -4.0189 |  |  | Job Completed | Deductional
31 |  |  | 4215410 | SNPS Site Trimming on Access & Cold Vent Area During Shutdown | SPU | Estimate | 65275400 | 4200137498 | 65275400 | 100 | 65275400 | 0 |  |  | Job Completed
32 |  | 19Q764/S | 4214895 | MWPS, Site Preparation For RMI ( Provide Scaffolding Materials) | SPU | Estimate | 300954800 | 4200137495 | 300954800 | 100 | 300954800 | 0 |  |  | Job Completed
33 |  | 19T727/SC | 19T727/SC | GTS-G - Trees Inventory and Site Clearing (Assist CST/PWK) | SPU | Estimate | 269362800 | 4200137145 | 269362800 | 100 | 269362800 | 0 |  |  | Job Completed
34 |  | 19P706/SC | 4229746 | To Perform Site Trimming Along Walkway Area for SUP to SMP and Muster Point 2 Area | SPU | Estimate | 150929100 | 4200136515 | 150929100 | 100 | 150929100 | 0 |  |  | Job Completed
35 |  | 17T456/SC | 4180615 | Install Potable Water Tank | SPU | Estimate | 972327100 | 4200136432 | 972327100 | [5 empty] | Job Completed
36 |  |  | 4207441 | Install Security Fence | SPU | Estimate | 216967399 | 4200133867 | 216967399 | 0 | 0 | -100 |  |  | Waiting Schedule
37 |  | 20T016/SC | 7256810 | Repair bundwall emergency pit GTS - F | SPU | Estimate | 61630564 | 4200137497 | 61630564 | 100 | 61630564 | 0 |  |  | Job Completed
38 |  | 19T339/SC | 4206436 | GTS F - Site Trimming Adjacent Well Walk Way | SPU | Estimate | 35935500 | 4200133746 | 35935500 | 100 | 35935500 | 0 |  |  | Job Completed
1 |  |  | 4201703 | Job site trimming ROW pipeline smp to GTS X | SPU | Estimate | 65275400 | 4200139230 | 65275400 | 100 | 65275400 | 0 |  |  | Job Completed
2 |  | 19T662/SC | 4213064 | Job GTS E Vegetation Growing to flowline | SPU | Estimate | 57115975 | 4200138170 | 57115975 | 100 | 57115975 | 0 |  |  | Job Completed
3 |  |  | 4215492 | Site Trimming Bushes North Fences | SPU | Estimate | 40797125 | 4200139242 | 40797125 | 100 | 40797125 | 0 |  |  | Job Completed
4 |  | 20T055/SC | 7258085 | Repair Bundwall Emergency Pit GTS - E | SPU | Estimate | 93323938.49 | 4200138357 | 93323938.49 | 100 | 93323938.49 | 0 |  |  | Job Completed
5 |  |  | 4213061 | GTS-AC Scrapper Site Trimming | SPU | Estimate | 69043766 | 4200135336 | 69043766 | 100 | 69043766 | 0 |  |  | Job Completed
6 |  |  | 4215850 | Site Clearing at GTS-R Walkway | SPU | Estimate | 48956550 | 4200139229 | 48956550 | 100 | 48956550 | 0 |  |  | Job Completed
7 |  | 20T023/SC | 7256813 | GTS E - Repair bundwall emergency pit | SPU | Estimate | 46697104 | 4200137607 | 46697104 | 100 | 46697104 | 0 |  |  | Job Completed
8 |  |  | 4219652 | MWPN - Site Priperation for RMI HAKURYU | SPU | Estimate | 101546700 | 4200139985 | 101546700 | 100 | 101546700 | 0 |  |  | Job Completed
9 |  |  | 4219682 | GTS - X Repair broken Bundwall of emergency pit | SPU | Estimate | 110359000 | 4200139678 | 110359000 | 100 | 110359000 | 0 |  |  | Job Completed
10 |  |  | 4219699 | GTS - E Repair bundwall of emergency pit | SPU | Estimate | 154796000 | 4200139808 | 154796000 | 100 | 154796000 | 0 |  |  | Job Completed
11 |  |  | 4219992 | GTS - G, Repair broken bundwall of emergency pit | SPU | Estimate | 197518200 | 4200140006 | 197518200 | 100 | 197518200 | 0 |  |  | Job Completed
12 |  |  | 4219991 | GTS - F, Repair broken bundwall of emergency pit | SPU | Estimate | 90773200 | 4200140459 | 90773200 | 100 | 90773200 | 0 |  |  | Job Completed
13 |  |  | 4220965 | GTS - J, Repair Bundwall Emergency Pit | SPU | Estimate | 104742513 | 4200140771 | 104742513 | 100 | 104742513 | 0 |  |  | Job Completed
14 |  | 20P146/SC | 0 | Repair Pedestal Shelter CGC - SPU | SPU | Estimate | 22762507 | 4200139196 | 22762507 | 100 | 22762507 | 0 |  |  | Job Completed
15 |  |  | 4180615/4224694 klarifikasi | TEMPORARY WATER LINE AND FACILITY FOR POTABLE WATER TANK | SPU | Actual | 25270300 | 4200142758 | 25270300 | 100 | 25270300 | 0 |  |  | Job Completed
16 |  |  | 4217876 | Found Vegetation at TN-14/G10 | SPU | Estimate | 45740100 | 4200141029 | 29946800 | 100 | 29946800 | 0 |  |  | Job Completed
17 |  |  | 4218561 | Floor Tile Replacement Restauran SPU | SPU | Estimate | 418751957 | 4200139919 | 418751957 | [5 empty] | Job Completed
18 |  |  | 4180615 | Dismantle Potable Water Tank - SPU | SPU | Estimate | 193650100 | 4200135940 | 193650100 | 100 | 193650100 | 0 |  |  | Job Completed
19 |  |  | 4221573 | SNPS fallen tree at walkway to TMP1 | SPU | Estimate | 39069100 | 4200141464 | 31307100 | 100 |  | 0 |  |  | Job Completed
20 |  |  | 4220303 | TMP-1 Trimming Emergency Pit | SPU | Actual | 36095900 | 4200142760 | 36095900 | 100 | 36095900 | 0 |  |  | Job Completed
|  |  | 7264309 | GTS-E, FOUND EMERGENCY PIT LEAK | SPU | Estimate | 62042700 | 4200141028 | 62042700 | 100 | 62042700 | 0 |  |  | Job Completed
|  |  | 4220275 | SPU, VEGETATION TRIMMING ON PROCESS AREA | SPU | Estimate | 147255000 | 4200141218 | 147255000 | 100 | 147255000 | 0 |  |  | Job Completed
|  |  | 7267582 | GTS - E, Found Emergency Pit Leak | SPU | Estimate | 61898080 | 4200142114 | [6 empty] | Job Completed |  |  |  | 10 | 6189808 | 50 | 30949040 | 40 | 24759232 |  |  | 100 | 61898080 | 0% | 0 | Job Completed | Belum Realese | ?
24 |  |  | 4211668 | Site Trimming at Jetty Riani | SPU | Estimate | 20284860 | 4200142155 | [6 empty] | Job Completed | [7 empty] | 30 | 6085458 | 20 | 4056972 | 50 | 10142430 | -50% | -10142430 | Work Onprogress | Belum Realese
|  |  | 4222839 | Additional Concrette Ramp - Bridge to Jetty | SPU | Estimate | 14441228 | 4200142181 | [6 empty] | Job Completed | [7 empty] | 100 | 14441228 |  |  | 100 | 14441228 | 0% | 0 | Job Completed | Belum Realese
26 | 14241472 |  | 4223707 | MODIFY SUCTION & OVERFLOW LINES PWT TANK | SPU | Estimate | 24047380 | 4200143092 | [6 empty] | Job Completed
1 | 14234895 |  | 4218561 | ADDITIONAL FLOOR TILE REPLECEMENT RESTAURANT SPU - SMS #2nd | SPU | Estimate | 27754809 | 4200143464 | [6 empty] | Job Completed
2 | 14242706 |  | 4224710 | GTS - E, EMERGENCY PIT BUNDWALL BREACH | SPU | Estimate | 82556504 | 4200143216 | [6 empty] | Job Completed
3 | 14243371 |  | 4225237 | GTS - F, Repair Bundwall Emergency Pit | SPU | Estimate | 84481195 | 4200143489 / 3700065831 | [6 empty] | Job Completed
4 | 14235178 |  | 4218761 | Camp, Site trimming wild grass at composite area | SPU | Actual | 25649750 | 4200143467 | 28150752 | [5 empty] | Job Completed
5 | 14234895 |  | 4218561 | ADDITIONAL WATER FAUCET FLOOR TILE REPLACEMENT RESTAURANT SPU - SMS #3rd | SPU | Actual | 2771400 | 4200143465 | [6 empty] | Job Completed
6 | 14242706 |  | 4224710 | GTS - E, ADDITIONAL EMERGENCY PIT BUNDWALL BREACH - SMS #2nd | SPU | Actual | 28362488 | 4200143466 | [6 empty] | Job Completed
7 | 17267053 |  | 7265765 | SMP, C-TRIMMING TREES FOR ACCESS TO MP2 | SPU | Actual | 33808100 | 3700066337 | 33808100 | [5 empty] | Job Completed
8 | 14239034 |  | 4221689 | FUA_WATER STAGNAT TRAFO AREA_SUP | SPU | Estimate | 19983602.4 | [7 empty] | Waiting info
9 | 14244023 |  | 4225797 | BASE FORKLIFT PARKING LOT | SPU | Estimate | 15979206.32 | 4200142098 / 3700066329 | [6 empty] | Job Completed
10 |  |  | 4223751 |  | SPU | Actual | 62614200 | 4200142180 / 3700065833 | [6 empty] | Job Completed |  |  | Done HOC 3.7.21
11 | 14243371 |  | 4225237 | Add GTS - F, Repair Bundwall Emergency Pit - SMS #2nd | SPU | Estimate | 35608536 | 4200143490 | [6 empty] | Job Completed
12 | 17273363 |  | 7271601 | FOUND EMERGENCY PIT HIGH VEGETATION | SPU | Estimate |  |  | 82041498 | [5 empty] | Job Completed |  |  | Done HOC 3.7.21
13 | 14243436 |  | 4225274 | Supply Sand Bag for Ballast Rig RAISIS (Site Preparation Wellcon TN-AA384/385/386) | SPU | Estimate | 69369300 |  | 91563300 | [5 empty] | Job Completed
14 | 14241472 |  | 4223707 - 2nd | Dismantle temporary water line and facility for potable water tank - SMS #2nd | SPU | Estimate | 48969725 | [7 empty] | Job Completed
15 |  |  | 4222903 | TMP-1, Barrier Fence Broken | SPU | Estimate | 99651640 | 4200141965 / 3700065832 | [6 empty] | Job Completed |  |  | Done HOC 3.7.21
16 | 14243436 |  | 4225274 - 2nd | Supply Sand Bag for Ballast Rig RAISIS (Site Preparation Wellcon TN-AA384/385/386) - SMS #2nd | SPU | Actual | 28305100 | [7 empty] | Job Completed
17 | 14245418 |  | 4226798 | Provide Revostrap for mitigation on leaking point at RC#96 | SPU | Actual | 28651400 | [7 empty] | Job Completed
18 | 14245168 |  | 4226612 | Install cargo strap | SPU | Actual | 8007700 | [7 empty] | Job Completed
19 | 14241620 |  | 4223802 | Repair subsidence walkway at GTS-A | SPU | Actual | 2706300 | [7 empty] | Job Completed
20 |  |  | 4223707_2 | GTS - TM-X Site clearing along adjacent walkway - SMS #2nd | SPU | Actual | 64431640 | [7 empty] | Job Completed
21 | 14246256 |  | 4227466 | TMP-1, SITE CLEARING ACCESS TO EMERGENCY PIT | SPU | Estimate | 25045680 | 3700066335 | [6 empty] | Job Completed
22 | 14246023 |  | 4227312 | REPAIR 16" T/L GTS F_GTS C_RC 96 | SPU | Estimate | 25101775 | [7 empty] | Canceled
23 |  |  | 4223043 | Perform Inspection as required TN-G473-91 Well Conn | SPU | Actual | 14072875 | [7 empty] | Job Completed
24 |  |  | 4227744 | Perform Ste trimming a long walkway proccess & flare area | SPU | Actual | 156155645 | [7 empty] | Job Completed
25 |  |  | 4227871 | Provide Revostrap | SPU | Actual | 55584600 | [7 empty] | Job Completed
26 | 17275495 |  | 7273818 | GTS-R, Found high vegetation at emergency pit | SPU | Actual | 43570920 | [7 empty] | Job Completed
27 | 17272309 |  | 7270546 | GTS-F, Perform site clearing for inspection access | SPU | Actual | 80705620 | [7 empty] | Job Completed
28 | 14246023 |  | 4227312 - 2nd | REPAIR 16" T/L GTS F_GTS C_RC 96 | SPU | Estimate | 170010900 | 3700066331 | [6 empty] | Job Completed
29 |  |  | 7274598 | GTS - F Bundwall Emergency PIT Broken - SPU Area | SPU | Estimate | 60788850 | [7 empty] | Job Completed
30 |  |  | 4226798 | Provide Revostrap - SMS #1st | SPU | Actual | 55584600 | [7 empty] | Job Completed
31 |  |  | 4227312 - 3rd | REPAIR 16" T/L GTS F_GTS C_RC 96 (Excavation w Equipment) | SPU | Estimate | 569857400 | [7 empty] | Job Completed
32 |  |  | 4225508 | Camp - Smoking Corner | SPU | Estimate | 229651181 | [7 empty] | Onprogress
33 |  |  | 4226798 - 2nd | Camp - Smoking Corner | SPU | Actual | 55584600 | [7 empty] | Job Completed
34 |  |  | 4222226 | GTS-H, Repair riser & Pipeline to TMP-1 | SPU | Actual | 133022151 | [7 empty] | Job Completed
35 |  |  | 4227885 | Site Trimming for access to cold vent at Snps | SPU | Actual | 61613800 | [7 empty] | Job Completed
36 |  |  | 4300636 | CST Assistance For RMI Tasha WPN 3 - SPU Area | SPU | Actual | 8577390 | [7 empty] | Job Completed
37 |  |  | 4220965 - Phase 2 | Site Trimming at Cold Vent GTS - TMx - SPU Area | SPU | Estimate | 145570800 | [7 empty] | Job Completed
38 |  |  | 4300162 | CAMP - Site Trimming Jetty Riyani - SPU Area | SPU | Actual | 21785460 | [7 empty] | Job Completed
39 |  |  | 4227873 | Perform site trimming Along to cold Vent area at GTS FX | SPU | Actual | 77903425 | [7 empty] | Onprogress
PWK/SPS 2019,2020 & 2021
1 |  |  | 4210325 | PlLIDCO Clamp Refurbishment (Seal Material Replacement) | SNP | Estimate | 1453292360 | 4200136465 | 1453292360 | 100 | 1453292360 | 0 | 0 |  | Job Completed
2 |  |  | 4210325 | Supporting Install material PLIDCO CLAMP | SNP | Estimate | 241516280 | 4200136987 | 241516280 | 100 | 241516280 | 0 | 0 |  | Job Completed
3 |  |  | 4208621 | Pembuatan dan Pemasangan Pagar Barikade di Kanal Tanjung Una | CPU | Estimate | 637157750 | 4200134702 | 637157750 | 100 | 637157750 | 0 | 0 |  | Job Completed
4 |  |  | 7248116 | Install Pipe Support at HYB Cluster, Gilbert Channal RC#86, HN for HU Gathering Line | CPA | Estimate | 483221975 | 4200136889 | 483221975 | 100 | 483221975 | 0 | 0 |  | Job Completed
5 |  |  | 7225019 | Installation Repair Embankment Failure at ROW Pipe 16" GTS-E | SPU | Estimate | 1371328090 | 4200137748 | 1371328090 | 96.14 |  |  |  |  | Job Completed
1 |  |  | 7256558 | CPA Installation Wooden Wolkway for Assist. Repair Pipe Support at HO Cluster & HTB Cluster | CPA | Estimate | 845066375 | 4200137976 | 845066375 | 100 | 845066375 | 0 |  |  | Job Completed
2 |  |  | 4218378 | Installation Barrier of Tanjung Una Cannal Batch#2 | CPU | Estimate | 584437100 | 0 | 584437100 | 100 | 584437100 | 0 |  |  | Job Completed
3 |  |  | 20MHK3B0121044A | Installation Over Flow Embankment at Gilbert Channel Site Preparation Well HYA 354 for exTambak #1 (wooden outlet). | CPA | Estimate | 349772710 | 4200137976 | 349772710 | 100 | 349772710 | 0 |  |  | Job Completed
4 |  |  | 7244299 | Sand cement bag for Pipe support gatheringline TM 47 to GTS 3, TM 46 to GTS 1 (CPU-TAMBORA Area) | CPU | Estimate | 1081040670 | 4200139975 | 1081040670 | 100 | 1081040670 | 0 |  |  | Job Completed
5 |  |  | 20MHK3B0121044A | Survey Level Bundwall & Investigation Tress at Embankment #1 & #2 Gilbert Cannal (Site Preparation Well HYA 354) | CPA | Estimate | 87275450 | 4200140139 | 87275450 | 100 | 87275450 | 0 |  |  | Job Completed
6 |  |  | 20MHK3B0121044A | Reinstatement Bundwall EX.TAMBAK #1 & #2 for Dumping Area Gilbert Cannal (Provision of 1 unit swamp excavator). | CPA | Estimate | 445251000 | 4200140191 | 445251000 | 100 | 445251000 | 0 |  |  | Job Completed
7 |  |  | 4221402 | Installation Over Flow Embankment ex.Tambak #2 & Shoring Bundwall ex.Tambak #1 2 at Gilbert Cannal (Site Preparation Well HYA 354) | CPA | Estimate | 250006790 | 4200141585 |  |  | 265606014.76 | 0 |  |  | Job Completed
8 |  |  | 20MHK3B0121044A | Installation of Filtrasi & Pipe 16IN Over Flow ex.Tambak #1 at Gilbert CannalL (Site Preparation Well HYA 354) | CPA | Estimate | 163783130 | 4200140403 | 163783130 | 100 | 163783130 | 0 |  |  | Job Completed
9 |  |  | 7244299 | Sand cement bag for Pipe support gatheringline TM 47 to GTS 3, TM 46 to GTS 1 (CPU-TAMBORA Area)_Additional | CPU | Actual | 42780790 | 4200142300 | 42780790 | 100 | 42780790 | 0 |  |  | Job Completed
10 |  |  | 7248118 | INSTALL WOODEN WALKWAY for SPEDING REPLACE PIPE 6 inch HLB to HL GATHERING LINE CPA AREA | CPA | Estimate | 131645800 | 4200140778 | 131645800 | 100 | 131645800 | 0 |  |  | Job Completed
11 |  |  | 7266352 | Installation Wooden Support & Sand Cement Bags for PS 80-81 at HN Cluster (CPA Area) | CPA | Estimate | 123324670 | 4200141334 | 123324670 | 100 | 123324670 | 0 |  |  | Job Completed
1 | 14240866 |  | 4223227 | Install Shelter and Bundwall at PK-6.3 #SMS-1st (Site Survey) | SNP | Actual | 14753175 |  |  | 100 |  | 0 |  |  | Job Completed
2 | 14240866 |  | 4223227 - 2nd | Install Shelter and Bundwall at PK-6.3 #SMS-2nd (Repair Bundwall) | SNP | Estimate | 361378935 | 4200144569 | [6 empty] | hold
3 | 14243151 |  | 4225051 | Excavation 20 inch OWT line from OBV 18 to NOWT for repair leaking | SNP | Actual | 143158500 | 4200143692 / 3700065881 | 229112525 |  |  | 0 |  |  | Job Completed
4 |  |  | 4223015 | Install Sedimen Fencing at ROW GTS-E to GTS-G_SPU_SMS #1st | SPU | Estimate | 540377420 | [7 empty] | Waiting info
5 | 14243151 |  | 4225051 - 2nd | Excavation 20 inch OWT line from OBV 18 to NOWT for repair leaking - SMS #2nd | SNP | Actual | 210219750 | 4200144714 / 3700065589 | [6 empty] | Job Completed
6 | 14246189 |  | 4227423 | Fabricatr concrete base for new HVAC at main building | SNP | Actual | 118459125 | [7 empty] | Onprogress
7 | 14246698 |  | 4227818 | Rebuild control box 6" venting line of 20"-DH-B1-2250 near fire sstation | SNP | Estimate | 21720046 | 4200144720 / 3700065592 | [6 empty] | Job Completed
8 | 14240866 |  | 4223227 - 3rd | Install Shelter and Bundwall at PK-6.3 #SMS-3rd (Install Shelter) | SNP | Estimate | 310437066 | 4200144569 | [6 empty] | Onprogress |  |  | WO 4225315 ada sub WO/Turunan dr Main WO/Super Order:4223227.
9 | 14301635 |  | 4301549 | Repair Retaining Wall at Main Gate | SNP | Estimate | 164753176.6 | [7 empty] | Awaiting Schedule
Total
[9 empty] | Total Progress | : |  |  | 45709792064.16
[9 empty] | HCA | :
[9 empty] | CPU | :
[9 empty] | SPU | :
[9 empty] | PWK/SPS | :
Note on I91: SMS INT
Note on H101: INT SMS Estimate
Note on H103: INT SMS Estimate
Note on H106: INT SMS Estimate
Note on H108: INT SMS Estimate
Note on H110: SMS Internl
Note on H119: natanegara: INT Estimate SMS
Note on H121: natanegara: SMS Estimasi INT
Note on H122: natanegara: SMS Estimasi INT
Note on H124: natanegara: INT SMS Estmate
Note on D206: natanegara: Deductional setelah muncul klarifikasi dari site engineering kalkulasi
Note on H332: INT SMS Estimate
Note on H334: natanegara: SMS Estimasi INT

## BMS
NO | NATIF. No. | ITEM No. | WO No. | AREA | CRO |  |  | DESCRIPTION | SMS |  |  | TOTAL PROGRESS 2020 |  | PROGRESS 2021 | [91 empty] | COMMULATIVE PROGRESS |  | DEVISIASI PROGRESS |  | JOB STATUS | REMARK |  | SMS |  | RAB |  | BUA | MR |  | weekly | jan | [20 empty] | May |  |  |  |  | Juni'
[14 empty] | 2021-01-01 | [7 empty] | 2021-02-01 | [7 empty] | 2021-03-01 | [9 empty] | 2021-04-01 | [7 empty] | 2021-05-01 | [9 empty] | 2021-06-01 | [9 empty] | 2021-07-01 | [9 empty] | 2021-08-01 | [7 empty] | 2021-09-01 | [25 empty] | Status : | Native | BOQ | Native | RAB |  | PO | Subcon | 2020 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 |  | 18 | 19 | 20 | 21 | 22 |  | 23 | 24 | 25 | 26 | 27 |  | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  | 37 | 38 | 39 | 40
[5 empty] | No. CRO | Value | Status |  | Type | Value | Status | % | Value | w1 |  | w2 |  | w3 |  | w4 |  | w5 |  | w6 |  | w7 |  | w8 |  | w9 |  | w10 |  | w11 |  | w12 |  | w13 |  | w14 |  | w15 |  | w16 |  | w17 |  | w18 |  | w19 |  | w20 |  | w21 |  | w22 |  | w23 |  | w24 |  | w25 |  | w26 |  | w27 |  | w28 |  | w29 |  | w30 |  | w31 |  | w32 |  | w33 |  | w34 |  | w35 |  | w36 |  | w37 |  | w38 |  | w39 |  | w40 | w41 | w42 | w43 | w44 | w45 | w46 | w47 | w48 | w49 | w49 | w50 | w51 | w52 | % | Value | % | Value
A | HCA AREA
1 |  |  |  | HCA |  |  |  |  | Estimate |  | Approval | [98 empty] | Waiting schedule |  |  | ok | ok
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 3245083636.36 | [96 empty] | Hold | Menunggu closing punchlist karena covid-19 |  | ok
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 32924570 | [96 empty] | Hold | Main WO dibuatkan WO perarea/terpisah |  | ok | ok | ok | ok | ok |  |  | ok | done
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 5410209076.7669 | [96 empty] | Job Completed | Jobs done, waiting punchlist and closing dok HOC |  | ok
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 19915925.25 | [31 empty] | 15071511 | [65 empty] | doc ready & CRO release' |  | ok | ok | ok | ok | ok |  |  | ok | [16 empty] | ok | ok | completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 139792937.4 | [13 empty] | 23777758.8 | [82 empty] | Job Completed | doc ready & CRO full reales |  | ok | ok | ok | ok | ok |  |  | ok | ok | ok | ok |  | ok | ok | ok | revisi sesuaikan BMS
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval | [5 empty] | 12529080 |  | 16161550 |  |  |  | 11367000 |  | 5933600 | [84 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  |  |  | ok | ok |  | ok | ok | completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 303483648.4854 |  | 20106042.5146 | [94 empty] | Job Completed |  |  | ok | ok | ok | ok |  |  |  | ok | ok | Completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 91805005.584 |  | 9106539.416 | [94 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | ok | Completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 56618841.11 |  | 19101907.208 | [5 empty] | 31416471.68 | [88 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | ok | ok | Completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval | [98 empty] | Waiting schedule |  |  | ok | ok | ok | ok | ok
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval | [98 empty] | Waiting schedule | SMS Internal Estimate
|  |  |  | HCA |  |  |  |  | Actual |  | Approval |  | 5439725 | [96 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | Completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 51171580.1625 |  | 2834394.8375 | [94 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | ok | Completed
|  |  |  | HCA |  |  |  |  | Actual |  | Approval |  | 100916250 | [96 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | Completed/close oddo
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval | [15 empty] | 17729225 |  | 31443700 |  | 15291398.5 |  | 30725616.5 |  | 47778775 |  | 51610165 |  | 13455125 |  | 20571584.4 |  | 12801163.1 |  | 14895105.24 |  |  |  | 10310948.398 | [61 empty] | waiting final dokumen ke 2 & CRO full realese) |  | ok | ok | ok | ok | ok | [9 empty] | ok | ok |  | ok | ok | ok | ok | ok |  | ok | ok | ok | ok |  | ok | Completed
|  |  |  | HCA |  |  |  |  | Actual |  | Approval |  | 11892713 | [96 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | Completed
|  |  |  | HCA |  |  |  |  | Actual |  | Approval |  | 23759700 |  | 6440125 | [94 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | ok | done Completed
|  |  |  | HCA |  |  |  |  | Estimate |  | Approval |  | 122773679.2 |  | 2308452.8 | [94 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok | ok | Completed
|  |  |  | HCA | [6 empty] | Approval | [7 empty] | 31649016.2739 | [5 empty] | 40156213.0854 |  | 30331297.55 |  | 16050569.95 |  | 21260209.69 |  | 13832471.35 | [76 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  |  | ok | ok |  |  | ok | ok | ok | ok |  | ok | ok | Completed
[9 empty] | Actual |  | Approval | [5 empty] | 21758900 |  | 34639150 | [5 empty] | 10879450 |  | 15818975 | [82 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  |  |  | ok | ok | - | - | ok | ok | Completed
[10 empty] | 15943250 | Approval | [5 empty] | 15943250 | [92 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  |  |  | ok | completed
[11 empty] | Approval |  |  |  | 43080075 |  |  |  | 11879850 | [90 empty] | Job Completed | Partial -1, done |  | ok | ok | ok | ok | ok |  |  |  | ok | ok | done partial
[11 empty] | Approval |  | 51539200 | [5 empty] | 7503000 | [93 empty] | ok | ok | ok | ok | ok |  |  | ok |  |  | ok | Completed
[11 empty] | Approval | [13 empty] | 13679468.2 |  | 18552061 |  | 37488870.088 |  | 47895342.912 |  | 38553090.6 |  | 24930622.18 |  | 32185234.992 |  | 46430784.2 |  | 32599382.88 |  | 27957123.5808 |  | 41203492.56 |  | 40874172.712 |  | 15859878.052 |  | 10166746.4112 |  | 11047751.292 |  | 4340827.5 |  | 3609629.64 | [53 empty] | doc ready summary ke 1-2 |  | ok | ok | ok | ok | ok | [8 empty] | ok | ok | ok |  | ok | ok | ok | ok | ok |  | ok | ok | ok | ok |  | ok | ok | ok | ok | ok | Completed
[11 empty] | Approval | [15 empty] | 11210390 |  |  |  | 10486035 | [55 empty] | 330940 | [22 empty] | Job Completed | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [9 empty] | ok | done | [34 empty] | ok
[11 empty] | Approval | [15 empty] | 5768200 |  | 1630800 |  | 2884100 |  | 1921200 | [76 empty] | Job Completed | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [9 empty] | ok | ok |  | ok | ok | Completed
[11 empty] | Approval | [21 empty] | 21003952.7 |  | 49280027.5 |  | 41180577.4167 |  | 60314808.5 |  | 76917506.5 |  | 78061537.4 |  | 20259724.8842 |  | 32198905.12 |  | 12642321.5 |  | 12311849.92 |  | 20327216.18 |  | 35638358.7 |  | 25162420.8792 | [21 empty] | 5937499.8 | [31 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [12 empty] | ok | ok | ok | ok | ok |  | ok | ok | ok | ok |  | ok | ok | ok | ok | ok | [12 empty] | ok
[11 empty] | Approval | [37 empty] | 13192300 |  | 11181820 |  | 25615873.4984 |  | 6376600 | [5 empty] | 35409420.7552 |  | 75404381.8326 |  | 119023286.4844 |  | 69528101.0039 |  | 72187611.3568 |  | 113357042.328 |  |  |  | 40368467.1883 | [13 empty] | 34620128.5429 | [23 empty] | ok | ok | ok | ok | ok | [23 empty] | ok | ok | ok | ok |  |  |  | ok | ok | ok | ok |  | ok | ok | ok | ok | [7 empty] | ok
[11 empty] | Review | [98 empty] | Waiting schedule | [31 empty] | ok | [7 empty] | ok | ok
[11 empty] | Approval | [98 empty] | Waiting schedule | cro sudah release |  | ok | ok | ok | ok | ok | [24 empty] | ok | [7 empty] | ok | ok
[11 empty] | Approval | [43 empty] | 46230551.792 |  | 2991774.288 | [53 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [25 empty] | ok | ok | Completed |  |  |  |  | ok | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [12 empty] | ok | Completed | [10 empty] | ok | [7 empty] | ok | ok
[11 empty] | Approval | [25 empty] | 12092239.8 |  | 28913586.45 |  | 9883453.4 |  | 28755869.6 |  | 20214517 |  | 15627065.4 |  | 23998212.6 | [63 empty] | ok | ok | ok | ok | ok | [14 empty] | ok | ok | ok |  | ok | ok | ok | ok |  | ok | ok | [7 empty] | ok | ok
[11 empty] | Approval | [23 empty] | 4939525 |  | 18257500 | [49 empty] | 500200 | [25 empty] | ok | ok | ok | ok | ok | [14 empty] | ok | ok | Completed | [7 empty] | ok | [7 empty] | ok | ok | [11 empty] | ok
[11 empty] | Approval | [39 empty] | 13192300 | [17 empty] | 11318668 | [5 empty] | 48124373.64 |  | 51165630.905 |  | 39072437.6324 | [11 empty] | 20033828.0415 | [19 empty] | cro sudah release |  | ok | ok | ok | ok | ok | [24 empty] | ok | [7 empty] | ok | ok |  | ok |  |  | ok | ok | ok
[11 empty] | Approval | [39 empty] | 5189100 |  |  |  | 4617640 | [27 empty] | 19626289 |  | 37290305.67 |  | 24843105.76 |  | 13209117.39 |  | 49041105 | [21 empty] | ok | ok | ok | ok | ok | [24 empty] | ok |  | ok | [5 empty] | ok | ok | [9 empty] | ok |  | ok | ok
[11 empty] | Approval | [99 empty] | canceled & replaced to wo 4226646 | [38 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [23 empty] | 15318775 | [77 empty] | ok | ok | ok | ok | ok | [14 empty] | ok | Completed | [16 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [27 empty] | 17388510 |  | 49848135 |  | 43575270 |  | 44427074 |  | 47197800 |  | 29843936 | [63 empty] | ok | ok | ok | ok | ok | [16 empty] | ok |  | ok | ok | ok | ok |  | ok | Completed | [7 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [27 empty] | 23195622 | [73 empty] | ok | ok | ok | ok | ok | [16 empty] | ok | Completed | [14 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [16 empty] | ok | Completed | [14 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [29 empty] | 4933200 |  | 2850800 | [67 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [18 empty] | ok | ok | Completed | [11 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [29 empty] | 5467800 |  | 4411250 | [9 empty] | 10879450 | [57 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [18 empty] | ok | ok | [5 empty] | ok | Completed | [5 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [31 empty] | 5719900 | [69 empty] | ok | ok | ok | ok | ok | [19 empty] | ok | Completed | [11 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [33 empty] | 21771550 |  | 20258300 | [63 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [20 empty] | ok | ok | Completed | [9 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [33 empty] | 7865600 | [65 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [20 empty] | ok | Completed | [10 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [33 empty] | 33323300 |  | 59652861.2 | [9 empty] | 6050340 | [53 empty] | cro sudah release dok sirkulasi |  | ok | ok | ok | ok | ok | [20 empty] | ok | ok |  | ok |  |  |  | ok |  |  |  |  | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [35 empty] | 25698025 |  | 5939925 | [61 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [21 empty] | ok |  | ok | Completed | [7 empty] | ok | ok | [11 empty] | ok | ok
[11 empty] | Approval | [71 empty] | 32934656.36 |  | 49861857.6 |  | 132985741.23 |  |  |  | 66881469.4 | [19 empty] | cro sudah release |  | ok | ok | ok | ok | ok | [32 empty] | ok | ok | [8 empty] | ok | ok |  | ok | ok
[11 empty] | Approval | [71 empty] | 25174650.066 |  | 79076815.374 |  | 153526465.108 |  | 183709833.6 |  | 35917944.8 | [21 empty] | ok | ok | ok | ok | ok | [32 empty] | ok | ok | [8 empty] | ok | ok |  | ok | ok
[11 empty] | Approval | [43 empty] | 65377546.5564 |  | 42181998.7728 |  | 28834869.9816 |  |  |  | 46074459.6464 | [11 empty] | 17404635.3596 | [35 empty] | cro sudah release dok sirkulasi |  | ok | ok | ok | ok | ok | [26 empty] | ok | ok |  | ok | - | ok | ok | ok |  |  |  |  | ok | [6 empty] | ok | ok
[11 empty] | Approval | [55 empty] | 33418640.2825 |  | 17564388 |  | 41599440 |  | 71488281.494 |  | 36614615.0655 |  |  |  | 26670732.918 |  | 46609495.072 |  | 73008448.933 | [5 empty] | 54121865.803 |  | 46257209.597 | [21 empty] | ok | ok | ok | ok | ok | [32 empty] | ok | ok |  | ok | ok | ok | ok |  | ok | ok | ok |  |  | ok | ok
[11 empty] | Approval | [45 empty] | 27790211.7597 |  | 21744068.1818 |  | 80475431.029 |  | 76029269.1468 |  | 81189095.8169 |  | 69944319.0152 |  | 73240485.4399 |  | 51663495.6599 | [39 empty] | cro sudah release dok sirkulasi |  | ok | ok | ok | ok | ok | [27 empty] | ok |  | ok | ok | ok | ok | ok |  | ok | ok | [8 empty] | ok
[11 empty] | Approval | [37 empty] | 30637550 |  | 20758500 | [59 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [23 empty] | ok | ok | [7 empty] | ok | ok | [11 empty] | ok
[11 empty] | Approval | [39 empty] | 4184330 | [59 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [23 empty] | ok | ok | Completed | [6 empty] | ok | ok | [11 empty] | ok
[11 empty] | Approval | [39 empty] | 11817375 | [19 empty] | 16742875 |  | 41331940 |  | 33444010 |  | 10066150 | [7 empty] | 5931415 | [25 empty] | Dok sirkulasi |  | ok | ok | ok | ok | ok | [24 empty] | ok | [10 empty] | - | ok | ok | ok | ok |  |  |  | ok |  | ok
[11 empty] | Approval | [43 empty] | 23759700 | [55 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [26 empty] | ok | Completed |  |  |  |  | ok | ok | [11 empty] | ok
[11 empty] | Approval | [45 empty] | 26260700 |  | 15201375 |  | 30720180 | [49 empty] | doc ready, sms initial blm ada dan cro actual |  | ok | ok | ok | ok | ok | [27 empty] | ok |  | ok | ok | Completed | ok | ok | [11 empty] | ok
[11 empty] | Approval | [45 empty] | 19852625 | [53 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [32 empty] | ok | ok | [11 empty] | ok
[11 empty] | Approval | [45 empty] | 9909923 | [53 empty] | doc ready & CRO full reales |  | ok | ok | ok | ok | ok | [27 empty] | ok | Completed |  |  |  | ok | ok | [11 empty] | ok
62 | [10 empty] | Approval | [47 empty] | 13591721.3 |  | 46473442.66 |  | 50514551.7 |  | 81165090.8 |  | 41267767.24 |  | 70111587.65 |  | 51394236.9 | [19 empty] | 17758192.5 | [19 empty] | cro sudah release dok sirkulasi |  | ok | ok | ok | ok | ok | [29 empty] | ok | ok | ok | ok | ok |  | ok | ok | [8 empty] | ok
[11 empty] | Approval | [49 empty] | 18631700 |  | 34948450 |  | 22806350 |  | 9391850 | [43 empty] | cro sudah release - finaly dok sirkulasi |  | ok | ok | ok | ok | ok | [30 empty] | ok | ok | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [49 empty] | 11379650 |  |  |  | 18319975 | [45 empty] | sirkulasi |  | ok | ok | ok | ok | ok | [30 empty] | ok | - | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [53 empty] | 11879850 |  | 12380050 | [43 empty] | sirkulasi |  | ok | ok | ok | ok | ok | [32 empty] | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [55 empty] | 20667950 |  | 22695847.65 |  | 26028580.375 | [7 empty] | 25068575.45 |  | 26350466.905 |  | 16063778.96 |  | 11666539.05 |  | 0 |  | 10894111.26 |  | 0 | [21 empty] | ok | ok | ok | ok | ok | [32 empty] | ok | ok |  | ok | ok |  |  |  | ok | ok | ok | ok |  | ok | ok
[11 empty] | Approval | [51 empty] | 27198625 |  | 7940725 | [45 empty] | Dok is done - menunggu CRO actual |  | ok | ok | ok | ok | ok | [31 empty] | ok | ok | ok | [11 empty] | ok
[11 empty] | Approval | [51 empty] | 24333950 |  | 43671001 |  | 62006864 | [43 empty] | sirkulasi |  | ok | ok | ok | ok | ok | [31 empty] | ok | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [55 empty] | 7878250 | [43 empty] | sirkulasi |  | ok | ok | ok | ok | ok | [33 empty] | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
[11 empty] | Approval | [63 empty] | 37322280 |  | 26262190 |  | 56862095 |  | 63045135 |  | 61734335 |  | 23786690 | [25 empty] | Dok sirkulasi |  | ok | ok | ok | ok | ok | [38 empty] | ok | ok | ok | ok | ok | ok |  | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
[11 empty] | Approval | [61 empty] | 26484800 | [37 empty] | sirkulasi |  | ok | ok | ok | ok | ok | [37 empty] | ok | Completed | [6 empty] | ok
[11 empty] | Review | [65 empty] | 3939125 | [35 empty] | ok | ok | ok | ok | ok | [39 empty] | ok | [5 empty] | ok
[11 empty] | Review | [69 empty] | 4759075 |  | 38372525 |  | 20995950 | [25 empty] | Dok sirkulasi |  | ok | ok | ok | ok | ok | [41 empty] | ok | ok | ok |  | ok
[11 empty] | Review | [69 empty] | 4945850 | [31 empty] | ok | ok | ok | ok | ok | [41 empty] | ok | Completed |  |  | ok
[11 empty] | Review | [69 empty] | 38987123 |  | 49452675 | [27 empty] | SMS Internal Estimate, covered WO 4225908, Install LPS (add) |  | ok | ok | ok | ok | ok | [41 empty] | ok | ok | Completed |  | ok
[11 empty] | Review | [75 empty] | 16988775 | [25 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
[11 empty] | Review | [75 empty] | 5078825 | [25 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
[11 empty] | Review | [75 empty] | 5119025 | [25 empty] | ok | ok | ok | ok | ok | [45 empty] | ok
B | CPU AREA
1 |  |  |  | CPU |  |  | Realese |  | Estimate |  | Approval |  | 139475228.5734 | [7 empty] | 26502064 | [5 empty] | 66313781.98 |  | 40909291.44 |  | 11709887.95 | [7 empty] | 20393179.8406 | [73 empty] | ok | ok | ok | ok | ok |  |  | ok | ok | ok | ok | ok | ok | ok | ok | ok |  |  |  | ok |  | ok | Completed
|  |  |  | CPU |  |  | Realese |  | Estimate |  | Approval |  | 343944585.058 |  | 17504460.942 |  | 12392538.72 |  | 54136573.87 | [93 empty] | ok | ok | ok | ok | ok |  |  | ok | ok | ok | ok | Completed
[7 empty] | Realese |  |  |  | Approval | [5 empty] | 7868747 | [95 empty] | ok | ok | ok | ok | ok |  |  |  |  | ok | completed
[7 empty] | Realese |  |  |  | Approval | [15 empty] | 1250.75 | [85 empty] | ok | ok | ok | ok | ok | [6 empty] | ok | ok |  | ok | completed
5 | [6 empty] | Realese |  |  |  | Approval | [19 empty] | 29043077.25 |  | 39141416.29 |  | 42592303.03 |  | 31265451.07 |  | 55525919.39 |  | 20205623.472 |  | 41037807.27 |  | 34701791.25 |  | 10921382.98 | [65 empty] | ok | ok | ok | ok | ok | [12 empty] | ok | ok | ok | ok | ok |  | ok | ok | ok | ok | Completed
6 | [6 empty] | Realese |  |  |  | Approval | [39 empty] | 30995919.9967 | [61 empty] | ok | ok | ok | ok | ok | [24 empty] | ok | Completed
7 | [6 empty] | Realese |  |  |  | Approval | [101 empty] | ok | ok | ok | ok | ok
8 | [6 empty] | Realese |  |  |  | Approval | [99 empty] | 22.03.21 start - done ( nilai awal 5.946.250 - revisi info p.budiman dialihkan ke Wo lain yang akan continue (new update CRO reales) |  | ok | ok | ok | ok | ok | [15 empty] | ok | Completed
9 | [6 empty] | Realese |  |  |  | Approval | [31 empty] | 6418375 | [69 empty] | ok | ok | ok | ok | ok | [19 empty] | ok | Completed
10 | [6 empty] | Realese |  |  |  | Approval | [37 empty] | 27637257.375 | [63 empty] | ok | ok | ok | ok | ok | [21 empty] | ok |  | ok | Completed
11 | [6 empty] | Realese |  |  |  | Approval | [39 empty] | 11617850 | [13 empty] | 4415409.32 | [19 empty] | -581864.65 |  | -893710.35 | [23 empty] | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [24 empty] | ok |  |  |  |  | ok | ok | - | ok | Completed | [9 empty] | ok |  | ok | Completed actual BOQ
12 | [6 empty] | Realese |  |  |  | Approval | [43 empty] | 42161400 | [29 empty] | -2649875 | [25 empty] | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [26 empty] | ok | Completed |  |  |  |  | ok | [10 empty] | ok | Completed actual BOQ
13 | [6 empty] | Realese |  |  |  | Review | [101 empty] | ok | ok | ok | ok | ok | [26 empty] | ok | Completed |  |  |  |  | ok
14 | [6 empty] | Realese |  |  |  | Approval | [61 empty] | 44730875 | [37 empty] | Wo Odoo 7273771, Rev. - |  | ok | ok | ok | ok | ok | [32 empty] | ok |  |  |  |  | ok | Completed
15 | [10 empty] | Approval | [47 empty] | 3577825.16 |  | 15205756.93 |  | 8944562.9 |  | 9481236.674 |  | 8944562.9 |  | 16457995.736 |  | 53667377.4 |  | 53667377.4 |  | 8944562.9 | [9 empty] | -8144163 | [25 empty] | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [29 empty] | ok | ok | ok | ok | ok |  | ok | ok | ok | ok |  |  |  |  | ok | Completed actual BOQ
16 | [10 empty] | Approval | [51 empty] | 23281750 |  | 34922625 | [19 empty] | -43062800 | [25 empty] | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [31 empty] | ok | ok | Completed | [9 empty] | ok | Completed actual BOQ
17 | [10 empty] | Approval | [55 empty] | 4473725 | [45 empty] | ok | ok | ok | ok | ok | [33 empty] | ok | Completed
18 | [10 empty] | Review | [59 empty] | 56644704 |  | 15107254.8 |  | 15107254.8 |  | 22640175 |  | 46454400 |  | 52591392 |  | 45172230 |  | 42205206 |  | 34038096.6 |  | 37772655 |  | 62958990 | [21 empty] | ok | ok | ok | ok | ok | [36 empty] | ok | ok | ok | ok | ok | ok | ok | ok |  | ok | ok
19 | [10 empty] | Review | [138 empty] | ok
20 | [10 empty] | Approval | [77 empty] | 2472925 | [23 empty] | ok | ok | ok | ok | ok | [32 empty] | ok | [13 empty] | ok | Completed Actual
21 | [10 empty] | Review | [61 empty] | 15491969 |  | 15491969 |  | 16317184.399 |  | 14666753.601 | [5 empty] | -30971956.0033 | [25 empty] | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [37 empty] | ok | ok | ok | ok |  |  | ok
22 | [10 empty] | Review
23 | [10 empty] | Approval | [99 empty] | Belum naik odoo - pengajuan invoice periode ags-sep
C | SPU AREA | [148 empty] | ok
1 |  |  |  | SPU |  |  | Realese |  | Estimate |  | Approval |  | 904264203 | [7 empty] | 14584906.5 | [91 empty] | ok | ok | ok | ok | ok |  |  | ok | ok | ok | ok | ok | completed | [24 empty] | ok
|  |  |  | SPU |  |  |  |  | Estimate |  | Approval | [98 empty] | Waiting schedule | [39 empty] | ok
|  |  |  | SPU |  |  |  |  | Estimate |  | Approval | [9 empty] | 209375979 | [5 empty] | 33562590.1875 |  |  |  | 4478892 |  | 7681009.8104 | [76 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [5 empty] | ok | ok | ok | ok | ok | ok |  | ok | ok | completed | [17 empty] | ok
|  |  |  | SPU |  |  |  |  | Estimate |  | Approval |  | 10142430 | [5 empty] | 10142430 | [93 empty] | ok | ok | ok | ok | ok |  |  | ok |  |  | ok | Completed | [25 empty] | ok
5 |  |  |  | SPU |  |  |  |  | Estimate |  | Approval | [9 empty] | 1444123 | [7 empty] | 5776491 | [81 empty] | 13.11.20 |  | ok | ok | ok | ok | ok | [5 empty] | ok | ok |  |  |  | ok | Completed | [20 empty] | ok
6 |  |  |  | SPU |  |  |  |  | Estimate |  | Approval | [101 empty] | ok | ok | ok | ok | ok | [5 empty] | ok | Completed | [25 empty] | ok
7 | [10 empty] | Approval | [19 empty] | 8326442.7 | [78 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [5 empty] | ok |  |  |  |  | ok |  |  | ok | Completed | [17 empty] | ok
[11 empty] | Approval | [15 empty] | 10349802.25 |  | 6209881.35 |  | 24658597.88 |  | 41338222.52 | [76 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [13 empty] | ok | ok | Completed | [16 empty] | ok
[11 empty] | Approval | [27 empty] | 26856571.8905 | [73 empty] | ok | ok | ok | ok | ok | [14 empty] | ok | ok | ok | Completed | [14 empty] | ok
[11 empty] | Approval | [98 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [15 empty] | ok | Completed | [15 empty] | ok
[11 empty] | Approval | [31 empty] | 2771400 | [66 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [19 empty] | ok | Completed | [11 empty] | ok
[11 empty] | Approval | [21 empty] | 28362488 | [76 empty] | Job Completed |  |  | ok | ok | ok | ok | ok | [14 empty] | ok | Completed | [16 empty] | ok
[11 empty] | Approval | [23 empty] | 33808100 | [49 empty] | -2501000 | [24 empty] | Job Completed | Deduction - setelah terima approval kalkulasi dari engineering site. (kelebihan pengakuan progress) |  | ok | ok | ok | ok | ok | [14 empty] | ok | Completed | [16 empty] | ok | [10 empty] | ok | Completed actual BOQ
[11 empty] | Review | [98 empty] | Waiting info |  |  | ok | ok | ok | ok | ok | [32 empty] | ok
[11 empty] | Approval | [27 empty] | 15979206.32 | [73 empty] | ok | ok | ok | ok | ok | [16 empty] | ok | Completed | [14 empty] | ok
[6 empty] | 62614200 |  |  |  |  | Approval | [23 empty] | 14521485.264 |  | 30054816 |  | 5515058.736 | [29 empty] | 1378764.684 |  |  |  | 11144075.316 | [39 empty] | ok | ok | ok | ok | ok | [14 empty] | ok | ok | ok | Completed | [14 empty] | ok |  |  | ok |  | ok | Completed
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [32 empty] | ok
[11 empty] | Approval | [31 empty] | 42802649 |  | 25867253.5998 |  | 13371595.4002 | [65 empty] | ok | ok | ok | ok | ok | [19 empty] | ok | ok | ok | Completed | [9 empty] | ok
[11 empty] | Approval | [31 empty] | 38153115 |  | 12206700 | [67 empty] | ok | ok | ok | ok | ok | [18 empty] | ok | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [31 empty] | 34978375 |  | 13991350 | [67 empty] | ok | ok | ok | ok | ok | [19 empty] | ok | ok | Completed | [10 empty] | ok
[11 empty] | Approval | [35 empty] | 63119348.776 |  | 36532291.224 | [63 empty] | ok | ok | ok | ok | ok | [21 empty] | ok |  | ok | Completed | [7 empty] | ok
[11 empty] | Approval | [99 empty] | Waiting info calculation & Natif Wo as per actual site |  | ok | ok | ok | ok | ok | [21 empty] | ok | Completed | [9 empty] | ok
[11 empty] | Approval | [35 empty] | 28651400 | [65 empty] | ok | ok | ok | ok | ok | [21 empty] | ok | Completed | [9 empty] | ok
[11 empty] | Approval | [35 empty] | 8007700 | [65 empty] | ok | ok | ok | ok | ok | [21 empty] | ok | Completed | [9 empty] | ok
[11 empty] | Approval | [37 empty] | 2706300 | [63 empty] | ok | ok | ok | ok | ok | [32 empty] | ok
[11 empty] | Review | [45 empty] | 22074279.864 | [55 empty] | ok | ok | ok | ok | ok | [26 empty] | ok | ok | Completed |  |  |  | ok
[11 empty] | Approval | [101 empty] | ok | ok | ok | ok | ok | [29 empty] | ok | Completed |  | ok
[65 empty] | 3514248.5 |  | -25101775 | [43 empty] | Deleted/cancel - digabung di SMS 2nd' |  | ok | ok | ok | ok | ok | [29 empty] | ok | ok | - | ok | ok | Completed
29 | [10 empty] | Review | [61 empty] | 14072875 | [37 empty] | Revisid BOQ Odoo |  | ok | ok | ok | ok | ok | [37 empty] | ok | Completed
30 | [10 empty] | Review | [51 empty] | 21861790.3 |  | 46846693.5 |  | 37477354.8 |  | 42162024.15 |  | 7807782.25 | [41 empty] | ok | ok | ok | ok | ok | [31 empty] | ok | ok | ok |  | ok | ok
31 | [10 empty] | Review | [53 empty] | 25013070 | [45 empty] | WO original 4300320 release 25.07.21 |  | ok | ok | ok | ok | ok | [31 empty] | ok | ok | Completed
32 | [10 empty] | Review | [75 empty] | 12522840 | [23 empty] | Pekerjaan selesai, menunggu aktualisasi dari engineering | [51 empty] | ok | Completed
33 | [10 empty] | Review | [53 empty] | 6456449.6 | [47 empty] | ok | ok | ok | ok | ok | [31 empty] | ok | ok | Completed | [11 empty] | ok
34 | [10 empty] | Approval | [53 empty] | 32302071 |  | 81605232 |  | 49303161 |  | 6800436 | [41 empty] | ok | ok | ok | ok | ok | [32 empty] | ok | ok |  | ok | ok | [8 empty] | ok
35 | [10 empty] | Review | [73 empty] | 15197212.5 |  | 33433867.5 | [23 empty] | Pekerjaan selesai, menunggu aktualisasi dari engineering |  | ok | ok | ok | ok | ok | [43 empty] | ok |  | ok | Completed
36 | [10 empty] | Review | [55 empty] | 55584600 | [45 empty] | ok | ok | ok | ok | ok | [33 empty] | ok | Completed | [10 empty] | ok
37 | [10 empty] | Review | [59 empty] | 97446840 |  | 108237720 |  | 112288540 |  | 52921740 |  | 112288540 |  | 63175000 | [31 empty] | ok | ok | ok | ok | ok | [36 empty] | ok | ok | ok | ok | [5 empty] | ok
38 | [10 empty] | Approval | [79 empty] | 39408564.185 | [71 empty] | ok
39 | [10 empty] | Review | [99 empty] | WO original 4227871 release 25.07.21 |  | ok | ok | ok | ok | ok | [36 empty] | ok | [8 empty] | ok
40 | [10 empty] | Review | [61 empty] | 53514706.292 |  | 28242391.292 |  | 18439284.115 |  | 32825769.301 | [33 empty] | ok | ok | ok | ok | ok | [37 empty] | ok | ok | ok | ok |  |  |  |  | ok
41 | [10 empty] | Review | [67 empty] | 9242070 | [5 empty] | 9242070 | [27 empty] | ok | ok | ok | ok | ok | [38 empty] | ok |  | ok |  | ok | ok |  | ok
42 | [10 empty] | Approval | [69 empty] | 8577390 | [77 empty] | ok |  |  |  | ok
43 | [10 empty] | Review | [69 empty] | 43671240 |  |  |  | 29114160 | [25 empty] | Pekerjaan selesai, menunggu aktualisasi dari engineering |  | ok | ok | ok | ok | ok | [41 empty] | ok | ok | ok |  | ok
44 | [10 empty] | Approval | [75 empty] | 16024240 | [23 empty] | Pekerjaan selesai, menunggu aktualisasi dari engineering | [51 empty] | ok | Completed
45 | [10 empty] | Review | [77 empty] | 41311100 |  | 12224040 | [21 empty] | ok | ok | ok | ok | ok | [46 empty] | ok
D | PWK AREA | [111 empty] | ok | ok | ok | ok | ok
1 |  |  |  | SPU |  |  | Realese |  | Estimate |  | Approval |  | 1318394825.726 |  |  |  | 52933264.274 | [92 empty] | Job Completed |  |  | ok | ok | ok | ok | ok |  |  | ok |  |  | ok | completed
2 | [10 empty] | Review | [101 empty] | ok | ok | ok | ok | ok | [5 empty] | ok | Completed
3 | [10 empty] | Approval | [71 empty] | 20986510 |  | 18136840 | [27 empty] | ok | ok | ok | ok | ok | [42 empty] | ok | ok
[11 empty] | Approval | [15 empty] | 14816050 |  | 50608200 |  | 46604075 |  | 49461261.75 |  | 56059413.25 |  | 15538025 |  | 4907275 | [7 empty] | -8881775 | [65 empty] | ok | ok | ok | ok | ok | [9 empty] | ok | ok |  | ok | ok | ok | ok | ok |  |  |  |  | ok | Completed actual BOQ
[11 empty] | Review | [101 empty] | ok | ok | ok | ok | ok
[11 empty] | Approval | [29 empty] | 8881775 |  | 44733175 |  | 46909350 |  | 27103025 |  | 44192825 |  | 31130600 | [11 empty] | 25374917 | [47 empty] | Ready dok HOC - Waiting CRO actual ; CRO Lama: 4200144714 ((WO 4225051: 'Excavation leaking OWT line for repair (2nd-SMS)-under kontrak lama: 4600005863)).à CRO/RO baru Nomer: 3700065589 (under new Kontrak : 4710004538) |  | ok | ok | ok | ok | ok | [18 empty] | ok | ok | ok | ok |  | ok | ok | [6 empty] | ok | Completed
[11 empty] | Review | [77 empty] | 14520402 |  | 29562647 | [21 empty] | ok | ok | ok | ok | ok | [46 empty] | ok
[11 empty] | Approval | [51 empty] | 12754736.15 |  | 8965309.35 | [45 empty] | Ready dok HOC - Waiting CRO actual,; CRO Lama: 4200144720 WO 4227818:^Rebuild control box 20" venting line.-under kontrak lama: 4600005863)).à CRO/RO baru nomer: 3700065592 (under new Kontrak : 4710004538) |  | ok | ok | ok | ok | ok | [31 empty] | ok | ok | Completed
[11 empty] | Approval | [77 empty] | 33129581.08 |  | 62607663 | [21 empty] | ok | ok | ok | ok | ok | [46 empty] | ok
[14 empty] | HCA |  | HCA |  | HCA |  | HCA |  | HCA | [7 empty] | HCA
[14 empty] | SPU |  | SPU |  | SPU |  | SPU |  | SPU | [7 empty] | SPU
[14 empty] | CPU |  | CPU |  | CPU |  | CPU |  | CPU | [7 empty] | CPU
[16 empty] | PWK |  | PWK |  | PWK |  | PWK | [7 empty] | PWK
Sales
total
Note on CH62: natanegara: Sisa margin
Note on CJ71: natanegara: dalam satu minggu mengerjakan volume additonal, jadi belum bisa dijual.

## SALES
NO | WO No. | CRO |  | DESCRIPTION | AREA | TOTAL SALES 2020 | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | SALES |  | TOTAL SALES |  | DEVISIASI PROGRESS | JOB STATUS | REMARK
[7 empty] | 2021-01-01 |  | 2021-02-01 |  | 2021-03-01 |  | 2021-04-01 |  | 2021-05-01 |  | 2021-06-01 |  | 2021-07-01 |  | 2021-08-01 |  | 2021-09-01 |  | 2021-10-01 |  | 2021-11-01 |  | 2021-12-01 |  | 2021
|  | No. CRO | Value |  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
A | HCA AREA
1
B | CPU AREA
1
C | SPU AREA
1
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
D | PWK & SPS AREA
1
2

## INVOICE
NO. | WO NO. | CRO |  | DESCRIPTION | AREA | TOTAL INVOICE 2020 | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | INVOICE |  | TOTAL INVOICE |  | DEVISIASI INVOICE | REMARK
[7 empty] | Jan 21 - Feb 21 |  | Feb 21 - Mar 21 |  | Mar 21 - Apr 21 |  | Apr 21 - May 21 |  | May 21 - Jun 21 |  | Jun 21 - Jul 21 |  | Jul 21 - Aug 21 |  | Aug 21 - Sep |  | Sep 21 - Oct 21 |  | Oct 21 - Nov 21 |  | Nov 21 - Des 21 |  | Des 21 - Jan 22 |  | 2021
|  | CRO No. | Value |  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
A | HCA AREA
[6 empty] | 5089483736 | [27 empty] | Menunggu final kalkulasi by eng
53826825
[6 empty] | 128255830 |  |  |  | 182069488 |  | 253128682.43 | [21 empty] | Completed Actual
[10 empty] | 45991230 | [23 empty] | Completed Deduction
[8 empty] | 323589691 | [25 empty] | Completed Partial
[8 empty] | 100911545 | [25 empty] | Completed Deduction
[8 empty] | 107137220 | [25 empty] | Completed Deduction
5439725
[10 empty] | 54005975 | [23 empty] | Completed Deduction
[8 empty] | 58398850 | [11 empty] | 42517400 | [13 empty] | Completed Deduction
80222780
[8 empty] | 11892713 | [25 empty] | Completed Actual
[12 empty] | 30199825 | [21 empty] | Completed Actual
[8 empty] | 125082132 | [25 empty] | Completed Deduction
[10 empty] | 234597969 | [23 empty] | Completed Deduction
[12 empty] | 83096475 | [21 empty] | Completed Deduction
[10 empty] | 15943250 | [23 empty] | Completed Actual
[10 empty] | 54959925 | [23 empty] | Completed Actual
[8 empty] | 59042200 | [25 empty] | Completed Actual
[8 empty] | 12380050 | [25 empty] | Completed Actual
[8 empty] | 18820175 | [25 empty] | Completed Actual
[8 empty] | 52174086 | [25 empty] | Completed Actual
[8 empty] | 48957525 | [25 empty] | Completed Actual
[8 empty] | 41079275 | [25 empty] | Completed Actual
30 |  |  |  |  | HCA
Completed Actual
[10 empty] | 12320200 | [23 empty] | Completed Actual
33
Completed Actual
[10 empty] | 11518950 | [23 empty] | Completed Actual
Completed Actual
[12 empty] | 291728035 | [7 empty] | 119892614.4 | [13 empty] | Completed Deduction
[5 empty] | HCA | [6 empty] | 33161252 | [21 empty] | Completed Actual
[5 empty] | HCA | [6 empty] | 12204300 | [21 empty] | Completed Actual
[5 empty] | HCA | [6 empty] | 23195622 | [21 empty] | Completed Actual
[5 empty] | HCA | [6 empty] | 23697225 | [21 empty] | Completed Deduction
[5 empty] | HCA | [6 empty] | 22027365 | [21 empty] | Completed Deduction
[5 empty] | HCA | [6 empty] | 248696872.62 | [7 empty] | 146163688.9 | [13 empty] | Completed Deduction
[5 empty] | HCA | [6 empty] | 7378050 | [21 empty] | Completed Actual
[5 empty] | HCA | [6 empty] | 15318775 | [21 empty] | Completed Actual
[5 empty] | HCA | [6 empty] | 97056215 | [21 empty] | Completed Deduction
[5 empty] | HCA | [6 empty] | 6440125 | [21 empty] | Completed Actual
[5 empty] | HCA | [14 empty] | 148339715 | [13 empty] | Completed Deduction
[5 empty] | HCA | [14 empty] | 135224510 | [13 empty] | Completed Deduction
[5 empty] | HCA | [14 empty] | 7784000 | [13 empty] | Completed Actual
[5 empty] | HCA | [14 empty] | 5719900 | [13 empty] | Completed Actual
[5 empty] | HCA | [16 empty] | 54834693 | [11 empty] | Completed Deduction
[5 empty] | HCA | [16 empty] | 20758500 | [11 empty] | Completed Deduction
[5 empty] | HCA | [16 empty] | 42029850 | [11 empty] | Completed Actual
[5 empty] | HCA | [16 empty] | 7865600 | [11 empty] | Completed Actual
[5 empty] | HCA | [16 empty] | 31637950 | [11 empty] | Completed Deduction
57 |  |  |  |  | HCA | [16 empty] | 102564269
58 |  |  |  |  | HCA | [16 empty] | 51396050 | [11 empty] | Completed Actual
59 |  |  |  |  | HCA | [16 empty] | 10460825 | [11 empty] | Completed Actual
60 |  |  |  |  | HCA | [16 empty] | 23759700 | [11 empty] | Completed Deduction
61 |  |  |  |  | HCA | [16 empty] | 19852625 | [11 empty] | Completed Deduction
62 |  |  |  |  | HCA | [16 empty] | 9909923 | [11 empty] | Completed Actual
B | CPU AREA
289773609
162504543
[8 empty] | 7868747 | [25 empty] | Completed Actual
5 | [7 empty] | 24044900 | [25 empty] | Completed Actual
6 | [7 empty] | 6446400 | [25 empty] | Completed Deduction
[12 empty] | 158314572 | [9 empty] | 146120200 | [11 empty] | Completed Actual
[22 empty] | 9947850 | [11 empty] | Completed Deduction
[22 empty] | 1000400 | [11 empty] | Completed Actual
[22 empty] | 6418375 | [11 empty] | Completed Actual
[22 empty] | 84481195 | [11 empty] | Completed Actual
C | SPU AREA
[12 empty] | 418751956.5 | [21 empty] | Completed
[10 empty] | 14441228 | [23 empty] | Completed
[10 empty] | 24047380 | [23 empty] | Completed
[12 empty] | 27754809 | [21 empty] | Completed
[8 empty] | 31307100 | [25 empty] | Completed
[8 empty] | 193650100 | [25 empty] | Completed
[8 empty] | 22762507 | [25 empty] | Completed
[8 empty] | 147255000 | [25 empty] | Completed
[8 empty] | 36095900 | [25 empty] | Completed
[8 empty] | 197518200 | [25 empty] | Completed
[8 empty] | 90773200 | [25 empty] | Completed
[8 empty] | 104742500 | [25 empty] | Completed
[8 empty] | 25270300 | [25 empty] | Completed
[8 empty] | 29946800 | [25 empty] | Completed
[8 empty] | 62042700 | [25 empty] | Completed
Completed
Completed
Completed
22 | [11 empty] | 61898080 | [21 empty] | Completed
23 | [11 empty] | 2771400 | [21 empty] | Completed
[20 empty] | 35608536 | [13 empty] | Completed
[22 empty] | 28345905 | [11 empty] | Completed
[22 empty] | 99651640 | [11 empty] | Completed
[22 empty] | 62614200 | [11 empty] | Completed
D | PWK AREA
3 | [7 empty] | 42780790 | [25 empty] | Completed
4 | [7 empty] | 250006790 | [25 empty] | Completed
5 | [7 empty] | 123324670 | [25 empty] | Completed
6
7
8 | [21 empty] | 229112525 | [11 empty] | Completed
9
10
11
12
13

## WORK ACTIVITY
No. | WO No. | CRO |  | Deskripsi | Remark
|  | CRO No. | Value
2020
1 |  |  |  |  | Done 18.03.20 Feri S, menunggu puchlist (pandemi covid 19)
2 |  |  |  |  | hold -
3 |  |  |  |  | start 5.11.19 - done November 2020, menunggu closing punchlist and handover dok
4 |  |  |  |  | menunggu drawing by bayu - done 16.04.21
5 |  |  |  |  | start 18.01.20 - Hold 18.03.20 - Start 26.07.20 by faruk - cont. start 29.12.20 rahmadi done 11.02.20 by Acong
6 |  |  |  |  | done 30.12.20 by rahmadi
7 |  |  |  |  | 20.11.20 - 12.12.20 done by faruk
8 |  |  |  |  | start 23.12..20 by A. Faruk - Done 6.1.21 faruk
9 |  |  |  |  | Start 21.11.20 Angga - Hold
10 |  |  |  |  | Start 21.12,.20 by A. Faruk
11 |  |  |  |  | Start 25.11.20 - angga- hold - close info pak fatkur
12 |  |  |  |  | done
13 |  |  |  |  | Start 26.12.20 - done by rommy - remaining 4 pohon menunggu ijin dari perhutanan-close info pak fatkur
14 |  |  |  |  | start sch. 3.12.20 - done
15 |  |  |  |  | Done 8.02.21
16 |  |  |  |  | done
17 |  |  |  |  | close
2021
Januari
1 |  |  |  |  | Start 7.1.21 Faruk - (hold cermat APD) cont. 12.01.21 - done 4.02.21 faruk
2 |  |  |  |  | Start 2.1.21 angga - hold 8.1.21 - done partial-1
3 |  |  |  |  | Start 4.1.21 Rahmadi - 11.1.21 done Siswanto
4 |  |  |  |  | Start 8.1.21 Rian survey - start trimming 11.01.21 rommi- Done Romi
5 |  |  |  |  | Start 7.1.21 Faruk - Done 10.03.21 Faruk
lockdown Area HCA - 21.01.2021 all team (dampak covid-19) s/d 29.01.21
Februari
1 |  |  |  |  | Start 11.2.2021 by Acong - Done 31.5.21 Faruk
2 |  |  |  |  | Start 16.02.21 karyani - 17.01.21 done karyani - add start & finish 26.2.21
3 | 4222912 |  |  |  | Start 16.02.21 angga/rahmadi/Acong - Done 26.04.21 Bayu,
4 |  |  |  |  | Start 16.02.21 - 17.02.21 romy (hold-pindah ke SNP)continue start 1.03.21 Bayu - done finish 3.03.21 Bayu
5 |  |  |  |  | Start 17.02.21 - done 20.04.21 - continue to phase 2nd / SMS 2nd Done
6 |  |  |  |  | Done 25.02.21 Arifin mane
7 |  |  |  |  | Start 27.02.21 Bayu - Finish 28.02.21 Done Actual
8 |  |  |  |  | Start 26.02.21 Arifin mane
Maret
1 |  |  |  |  | Start 2.03.21 Budiman/Ahmad Nasir - 26.04.21
2 | 4218761 |  |  | Site trimming wild grass at composite area | Start 7.03.21 Suhendriyono - Done 12.03.21
3 |  |  |  |  | Start 8.03.21 Rahmady - Done 31.5.21 Faruk
4 |  |  |  |  | Start 13.03.21 Suhendriyono - Done 31.03.21 Arifin
5 |  |  |  |  | Start 19.03.21 Bayu - Done 23.03.21
7 | 4223751 |  |  | Tree Trimming guardrail and turnstill - SPU | Start 17.03.21 Siswanto - Done 26.03.21
8 | 7265765 |  |  |  | 12.03.21 - Done 16.03 SISwanto
9 |  |  |  |  | Start 19.03.21 on site installed - angga 4.5.21 done
10 |  |  |  |  | Start 16.03.21 - 18.03.21 Bayu
11 |  |  |  |  | Start 28.03.21 - syahrudin info validate 30.3.21 - Done 30.04.21 Siswanto
12 |  |  |  |  | Start 27.03.21 - siswanto - 31.03.21 done
13 |  |  |  |  | Start 30.03.21 angga - done
April
1 |  |  |  |  | Start 1.04.21 Arifin - Done
2 |  |  |  |  | Start 05.04.21 Rian - finish 6.04.21
3 |  |  |  |  | Start 4.04.21 (4 manpower helper to rig raisa) done -add soil bag
4 |  |  |  |  | Start 9.04.21 by Rian - hold 11.04..21 - start 18.05.21 -19.05.21 Done angga
5 |  |  |  |  | Start 09.04.21 rahmadi - done 11.04.21 rahmadi
6 |  |  |  |  | Start 15.04.21 rian - Done 24.04.21 Rian
7 |  |  |  |  | Start 15.04.21 rian -19.04.21
8 |  |  |  |  | SMS 1st done - ada add SMS 2nd done
9 | 4226822 |  |  | HW - HL Perform site trimming high vegetation for inspection access | Start 25.04.21 Rian - done 30.04.21
10 |  |  |  |  | Start 28.04.2021 Rahmadi -
May
1 |  |  |  |  | Start 1.05.21 - Ryan - 5.05.21 Done
2 |  |  |  |  | Start 1.05.21 - Angga - 17.05.21 done
3 | 4225908 |  |  |  | Start 8.05.21 Siswanto - hold - Done 17.08.21 rian
4 |  |  |  | SPU - lockdown mulai tanggal 10.05.21
5 |  |  |  |  | Start Rommy 20.05.21 - Done Romi
6 |  |  |  |  | Start Rommy 20.05.21 - done 27.05.21 romi
7 |  |  |  | Leaking PWHT - CPU | Start 16.05.21 Budiman - Done
8 |  |  |  | Site trimming at Halipad CPU | Start 15.05.21 Budiman (16.05.21 Hold, moved to PWHT leaking - progress 30%
9 |  |  |  | Site trimming Bundari fence CPU | start 12.05.21 - 14.05.21 done 100% by Budiman
10 |  |  |  |  | Start 24.05.21 Angga - done 27.5.21 angga
11 |  |  |  |  | Start 28.05.21 angga - 9.06.21 angga, done
12 |  |  |  |  | Start 28.05.21 rian - 30.5.21 Done Rian
13 |  |  |  | BSB, install plafon' | Start 31.05.21 rian -1.06.21 rian Done
Juni
1 | 4188686 - 3rd |  |  |  | Start 1.6.21 siswanto/faruk -hold tgl 12.7.21 - starting 16.09.21 Imam -
2 | 4223868 - 2nd |  |  |  | Start 1.6.21 siswanto/faruk - hold tgl 12.7.21
3 | 14246361 |  |  |  | Start 8.6.21 Romy - Done 27.06.21 Romi
4 | 4227818 |  |  |  | Start 13.06.21 Mr. Acong - 17.06 acong Done
5 | 7258712 |  |  |  | Start 13.06.21 Angga - 19.06.21 angga Done
6 | 4224696 |  |  |  | Start 10.06.21 Angga - cont. 20.6.21 - Done 22.06.21 angga
7 | 4227476 |  |  |  | Start 23.06.21 anggga - Done 27.06.21 Angga
8 | 4227601 |  |  |  | Start 25.06.21 Bayu - hold tgl 12.07.21 -start kembali 26.07.21 A. Faruk -
9 | 4228201 |  |  | Site survey HN | Start 24.06.21 - 25.06.21 Done menunggu info dishut
Juli
1 | 4225908 |  |  |  | Start 5.7.21 Rian - (ada additional foundation untuk LPS dan gayud 1 titik ) - Done 15.08.21 rian
2 | 4227885 |  |  | Site survey site trimming jalur pipa cold vent di SNPS - SPU (estimasi sd 7 hari) | Start 7.7.2021 Arifin - Done.
3 | 4222226 |  |  | Site survey clearing and install sand bags GTS H - SPU | Start 7.7.2021 Arifin - Done.
4 | 210380/VH |  |  | Supply sandbag HCA for rig yani | Start 15.07.21 fabrikasi - Done 18.07.21
5 | 4222226 |  |  | Supply sandbag SPU | Start 13.07.21 fabrikasi - Done 6.08.21 Hendriyono
6 | 4225491 |  |  |  | Start 15.07.21 transfer material ke CPU - start 27.07.21 ahmad Nasir -
7 | 7270368 - 2nd |  |  |  | Start 15.07.21 Budiman - Done 4.08.21 A Nasir
8 | 4300260 |  |  |  | Start 21.07.21 romi - Done 22.08.21
9 | 4227312 - 3rd |  |  |  | Start 10.07.21 mobilisasi. 11.07.21 on site - Done 9.08.21 Arifin mane (demob)
10 | 7266665 |  |  | PJC atap keropos | Done 100% 23.07.21 Ahmad nasir
Agustus
1 | 210398/VH |  |  | Site survey penegaan pohon di HEA | 2.08.21 Angga - menunggu info kelanjutan dari p.fatkur, Done 7.8.21 Angga
2 | 4300550 - 2nd |  |  | HN Cluster, Perform Cutting trees - SMS #2nd | Start 13.08.21 Angga - Done 24.08.21 angga
3 |  |  |  | Revostrap, dikembalikan 2 pc (menunggu diaktualkan) excel & Odoo | 7.08.21 Arifin eng
4 | 4223227 - 2nd |  |  | Install Shelter and Bundwall at PK-6.3 #SMS-2nd (Repair Bundwall) | Start 18.08.21 Imam - hold menunggu kesiapan team eni untuk removing elektrical JB Gas detektor
5 | 7274598 |  |  |  | Start 23.08.21 suhendriyono - 29 agustus 21 done.
6 |  |  |  | Perform Site trimming to along Walkway & burn pit area, at GTS -R | Start 26.08.21 arifin mane - 02.09.21 - sama dgn cover wo 7273818
7 | 4300550 - 3rd |  |  | HN Cluster, Perform Cutting trees - SMS #3rd | Start 26.08.21 angga - Done 26.08.21
8 | 4223227 - 3rd |  |  |  | Start 30.08.21 team bpn workshop -
SEPTEMBER
1 | 210448/VH |  |  |  | Start 1.09.21 angga - Done 03.09.21
2 |  |  |  |  | start 1.09.21 - 02.09.21 arifin mane - cover WO 7273818
3 | 4227423 |  |  |  | Start 9/9/2021 Acong -
4 |  |  |  |  | Start 4.09.21 Arifin mane -
5 |  |  |  | Smoking corner SPU | Start 12.09.21 siswanto
6 |  |  |  |  | lanjut jalan kembali 17.09.21 arifin mane -

## DTR control
No. | Wo No. |  | Date Sent | Data Received | Jobs Ket. | Remark
1 | 4222846 | Swcr, Natif, HOC & SMS actual original |  | 2021-01-04 |  | done completed dok
2 | 7266763 | SMS Actual, Swcr, HOC, FAC, Resume daily, & dokumentasi |  | 2021-01-04 |  | done, SWCR Belum ada
3 |  | SMS Actual, partial AC, Dokumentasi, Resume daily, Summary progress final dgn timesheet & Deductional note | 2021-01-06 | 2021-01-18 |  | Done partial actual
4 |  | Actual Partial SMS, patial AC, Dokumentasi, Resume daily, Summary progress dgn timesheet | 2021-01-06 | 2021-01-18 |  | Done partial, Natif approval belum ada
5 |  | SMS actual, FAC, HOC, SWCR, Dokumentasi, Resume daily, Summary progress dgn ts & deductional note | 2020-01-06 | 2021-01-18 |  | HOC belum approval TTH HCA
6 |  | SMS Actual, Swcr, HOC, FAC, Resume daily, Summary Progress dgn ts & dokumentasi | 2020-01-06 | 2021-01-18 |  | HOC & SMS Actual Belum approve TTH HCA |  | Supv Done. Sirkulasi ke Supt 15.01.21 terlampir dgn Fax No.
7 |  | SMS Actual, HOC, FAC, Dokumentasi, Resume daily, Summary progress final dgn timesheet & Deductional note | 2020-01-06 |  |  | TR #1
8 |  | Partial SMS Actual, PAC, Resume daily, Summary Progress dgn ts & dokumentasi | 2021-01-08 |  |  | HGD
9 |  | SMS actual, FAC, HOC, SWCR, Dokumentasi, Resume daily, Summary progress dgn ts & deductional note | 2021-01-08 | 2021-01-18 |  | HOC belum approval TTH HCA
10 |  | Summary progress & TS |  | 2021-01-09 |  | kurang SMS act, FAC HOC Natif apv
11 |  | SMS actual, FAC, HOC, SWCR, Dokumentasi, Resume daily, Summary progress dgn ts |  | 2021-02-13 |  | Assist GNS Scaffold
12 | 4221650 | SMS actual, FAC, HOC, SWCR, Dokumentasi, Resume daily, Summary progress dgn ts |  | 2021-01-18 |  | HOC belum approval TTH HCA
13 | 4222951 | SWCR, Natif, FAC, HOC & SMS actual original |  | 2021-01-21 |  | Done, completed
14 | 4221009 | SMS partial actual, PAC,dokumentasi, resum daily & Summary progress |  | 2021-01-21 |  | Done partial
15 | 4221039 | SMS Actual BQ, Deductional, FAC HOC, Dokumentasi, Summary Progress, Daily Activitie & Fax No. | 2021-12-02 |  | HDL 4 Trimming
| 4188686 | SMS Actual BQ, FAC Partial- HOC, Dokumentasi, Summary Progress & Fax No. ( revsi jadi progress partial - ref.file excel) | 2021-12-02 |  | Cluster SNP
| 7261453 | SMS Actual BQ, FAC HOC, Dokumentasi, Summary Progress & Fax No. | 2021-12-02 |  | HZC 2nd
| 4219719 | SMS Parial Actual BQ(1st), FAC Partial, Dokumentasi, Summary Progress & Fax No. | 2021-12-02 |  | HGD
| 4223504 | SMS Actual BQ, FAC HOC, Dokumentasi, Summary Progress & Fax No. | 2021-12-02 |  | HTC
| 4215747 | SMS Parial Actual BQ(1st), PAC, Dokumentasi, Summary Progress & Fax No. (revisi - final progress 100%) | 2021-12-02 |  | HOA
| 4205608 | Summary Progress, Daily activitie & Dokumentasi | 2021-12-02 |  | HDL IV Bundwall
| 4223544 | SMS Actual, FAC HOC, SWCR, Duductional, Time sheet daily & Summary progress |  | 17/2/21 | Trafo BSB | Done, completed
| 4221650 | HOC |  | 17/2/21 | BSB roof | Done, completed ( masih ada sms 2 untuk perbaikan plafon,material on site)
| 4221750 | HOC |  | 17/2/21 | HP 2 | Done completed
| 4224209 | HOC |  | 17/2/21 | hgl switchgear | done completed
| 4224082 | SMS Actual, FAC HOC, SWCR, Duductional, Time sheet daily & Summary progress |  | 17/2/21 | Assist Scaffold. | done completed
| 4221039 | SMS Actual, FAC HOC, SWCR, Duductional, Time sheet daily |  | 21/2/21 | HDL IV Trimming | done completed
| 4213661 | Summary Progress claim |  | 21/2/21 | HWTA #2nd | done completed
| 4205608 | Summary Progress claim |  | 21/2/21 | HDL IV Bundwall
| 4188686 | PAC PHOC, Summary claim ke 2 partial, SWCR |  | 21/2/21 | Cluster SNP | remaining daily report & sms actual , deductional
| 4219719 | PAC, Summary Progress, Daily timesheet, swcr, SMS actual partial |  | 21/2/21 | HGD trimming | Done
| 4223868 | SMS Estimate |  | 21/2/21 | Sirap roof tunu | Done
| 4221692 | HOC & SMS Actual |  | 21/2/21 | LP #1 | done Completed
| 4222976 | SMS actual BOQ | 23/2/21 |  |  | Resubmited
| 4225298 | SMS Actual, FAC HOC, SWCR, Time sheet daily & Summary progress | 23/2/21 |  |  | CPA Control room
| 4215747 | SMS Parial Actual BQ (1st), PAC, Dokumentasi, Summary Progress & Fax No. (revisi - final progress 100%) |  | 25/2/21 | HOA | Done Completed
March
37 |  | Daily report, summary weekly & monthly, progress claim ke-satu | 2021-09-03 |  | Tunu #2nd | resubmited 12/3/21
|  | SMS Actual & BOQ,No Fax 0015, Cover later, Summary weekly & montly, progress claim ke -tiga | 2021-09-03 |  | Senipah #1st
|  | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim ke satu | 2021-09-03 |  | WHP #2nd | resubmited
|  | SMS actual & BOQ, No Fax, FAC & HOC, Summary wekly & monthly, Progress claim, SWCR, timesheet daily, report dokumentasi | 2021-09-03 |  | CPAControl room | resubmited 12/3/21
|  | SMS actual & BOQ, No Fax, FAC & HOC, Summary wekly & monthly, Progress claim, SWCR, timesheet daily, report dokumentasi | 2021-09-03 |  | HLA
|  | SMS actual & BOQ, No Fax, FAC & HOC, Summary wekly & monthly, Progress claim, SWCR, timesheet daily, report dokumentasi | 2021-09-03 |  | HY
|  | SMS Actual & BOQ, No Fax, Cover later (belum ada Natif Wo validate) | 2021-09-03 |  | HGL | Belum ada natif WO approval dari asst planner
| 4205608 | SMS Actual & BOQ, No Fax,cover latter, FAC & HOC | 2021-12-03 |  | Bundwall #2nd
| 4205608 | SMS Actual & BOQ, No Fax,cover latter, FAC & HOC,SWCR,Daily report & timesheet, deductional | 2021-12-03 |  | Bundwall #1nd
| 4222912 | Daily report, summary weekly & monthly, progress claim ke-satu | 2021-12-03 |  | Pipeyard 2 - partial ke 1
| 7246456 | SMS Estimate, Natif WO Approval |  | 13/3/2021 | HDL IV Repair Fence
| 4207186 | SMS Estimate, Natif WO Approval |  | 13/3/2021 | HDL IV Repair Fence
49 | 17269182 | SMS Actual, Fax No, SWCR, HOC FAC, weekly,monthly, claim, daily report dan dokumentasi |  | 13/3/2021 | HTC | Done
50 | 4222976 | SMS actual & BOQ |  | 15/3/2021 | HGL MCT | Done
51 | 4225466 | SMS Actual, SWCR, FAC HOC, Weekly monthl & claim progress,timesheet, Natif WO |  | 15/3/2021 | HY | Done, HOC belum ttd RSES
52 | 4225907 | SMS Estimate, No fax, cover later, dwg. Natification | 15/3/2021 |  | Guyed
53 | 4222976 | Natif WO | 15/3/2021 |  | HGL | Resubmited
54 | 4225466 | HOC | 15/3/2021 |  | HY | Resubmited
55 | 4205608 | No Fax,cover latter, FAC & HOC |  | 20/3/2021 | Bundwall #2nd | kurang SMS ACTUAL kee RSES
56 | 4205608 | SMS Actual, BOQ, No Fax,cover latter, FAC & HOC,SWCR,Daily report & timesheet, deductional |  | 20/3/2021 | Bundwall #1nd | Done
57 | 4225907 | SMS Estimate, No fax, cover later, dwg. Natification |  | 20/3/2021 | Guyed
58 |  | SMS actual & BOQ, No Fax, FAC & HOC, Summary wekly & monthly, Progress claim, SWCR, timesheet daily, report dokumentasi |  | 20/3/2021 | CPAControl room | done
59 |  | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim, swcr & daily report | 27/03/2021 |  | HGC
60 |  | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim, swcr & daily report | 27/03/2021 |  | HGB - HGC
April
61 | 4224348 | SMS approval |  | 2021-06-04 | Repair rood #sms-3
62 | 4224348 | SMS approval |  | 2021-06-04 | Repair rood #sms-2
63 | 4224348 | SMS approval |  | 2021-06-04 | Repair rood #sms-1
64 | 4225834 | SMS Approval |  | 2021-06-04 | hooper
65 | 4221038 | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim, swcr & daily report |  | 2021-06-04 | HLA-HLB | HOC belum di sign oleh RSES
66 | 4217425 | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim, swcr & daily report |  | 2021-06-04 | WHP SMS-2 | Done
67 | 4188686 | Summari ke satu |  | 2021-06-04 | Tunu #2nd | Done
68 | 4222912 | Summary progress, daily aktifitas dan daily report ke-satu |  | 2021-06-04 | barbed layer | Done
69 | 4204886 | SMS Actual BOQ, No Fax, FAC HOC, Summary weekly Monthly, Progress claim, Dokumentasi, Daily report | 14/4/2021 |  | CPA Fresh water line
70 | 4222912 | Summary weekly, Monthly, Progress claim ke dua, daily report | 14/4/2021 |  | Pipe yard
71 | 4223868 | Summary weekly, Monthly, Progress claim ke Satu, daily report | 14/4/2021 | 16/4/2021 | Siraf roof tunu 1st
72 | 4204886 | Summary weekly, Monthly, Progress claim ke 3, (HOC FAC SWCR-copy) | 14/4/2021 | 16/4/2021 | cluster senipah 1st | done
73 | 4225834 | Summary weekly, Monthly, Progress claim ke 1 | 14/4/2021 | 16/4/2021 | Hooper barge
74 | 4225907 | Summary weekly, Monthly, Progress claim ke 1 | 14/4/2021 |  | Guyed
75 | 4204886 | Summary weekly, Monthly, Progress claim ke 2 | 14/4/2021 | 16/4/2021 | Cluster tunu 2nd
76 | 7272212 | Summary weekly, monthly, progress claim, daily manpower, timesheet & daily report |  | 19/4/2021 | puring concrete | done
77 | 4225948 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 16/4/2021 | HGB-HGC | done
78 | 4205608 | SMS actual Approval |  | 16/4/2021 | Control box #2nd | done
79 | 4225965 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 16/4/2021 | HGC-trimming | done
80 | 7272067 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 16/4/2021 | HQ-Trimming | done
81 | 7271811 | SMS Actual & BOQ, No Fax, FAC & HOC, Summary weekly & Monthly, progress claim, swcr & daily report | 2021-05-04 | 19/04/2021 | CPA roof repair | done
82 | 4225466 | HOC Approval |  | 19/04/2021 | HLA-HLB | done
83 | 4225051 | Summary progress weekly,montly,claim, Pac, timesheet |  | 26/04/2021 | SPS excavation | done
84 | 7261453 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 29/04/2021 | HZC-HKA | done
85 | 4225907 | Summary progress weekly,monthly,claim, daily activitas, time sheet |  | 29/04/2021 | guyed | done
May
86 | 4226526 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 2021-03-05 | HN | done
87 | 4213148 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim |  | 2021-03-05 | HN | done
88 | 4222912 | Summary weekly,monthly,claim, dokumentasi, timesheet |  | 2021-04-05 | pipeyard
89 | 4225834 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim | 2021-04-05 |  | Barge | resubmited HOC to RSES
90 | 4226822 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim | 2021-04-05 | 19/5/2021 | HW-HL | resubmited HOC,SMS Actual,summary progress to RSES
91 | 4225907 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, SWCR, Daily actifity, progress weekly, monthly, claim | 2021-04-05 | 19/5/2021 | guyed | resubmited HOC to RSES
92 | 4226931 | No Fax, SMS Actual BQ, Natif WO, FAC HOC, Daily actifity, progress weekly, monthly, claim | 2021-07-05 | 19/5/2021 | asst scafolding | resubmited HOC,SMS Actual,summary progress to RSES
93 | 4188686 | Summary claim ke-3, weekly report |  | 24/5/21 | Cluster tunu 2nd | done
94 | 4225907 | HOC Approval |  | 24/5/21 | guyed wire | done
95 | 4223868 | Summary progress claim ke-2, weekly report |  | 24/5/21 | Sirap roof tunu | done
96 | 4226931 | SMS Actual, HOC approval |  | 24/5/21 | asst scafolding | done
97 | 4226822 | SMS actual, SWCR, HOC approval |  | 24/5/21 | HW-HL | done
98 | 4193363 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 27/5/2021 |  | HFA -to burn pit
99 | 4226400 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 27/5/2021 |  | HFA -HTC
100 | 4226931 | resubmited monthly progress | 27/5/2021 | 30/5/21 | asst scafolding | done
101 | 7272018 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 29/5/2021 |  | HA
102 | 7246456 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 29/5/2021 |  | HDL IV fance
Juni
103 | 4224348 | summary progress claim,weekly,monthly ke 1 | 2021-01-06 | 8/6/20-21 | Pipe yard Zona F | done
104 | 4227542 | SMS Estimate cleaning Ditch pipe yard | 2021-01-06 | 8/6/20-21 | Pipe yard | done
105 | 4227417 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 2021-03-06 |  | HGL
106 | 4221650 - 2nd | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi | 2021-03-06 |  | BSB
107 | 7272018 | timesheet,weekly,monthly & Claim |  | 8/6/20-21 | HA trimming | done | waiting SMS actual, fac hoc
108 | 4226400 | timesheet,weekly,monthly & Claim |  | 8/6/20-21 | HFA -HTC | done | waiting SMS actual, fac hoc
109 | 4193363 | timesheet,weekly,monthly & Claim |  | 8/6/20-21 | HFA -to burn pit | done | waiting SMS actual, fac hoc
110 | 4204886 | timesheet,weekly,monthly, Claim drawings |  | 8/6/20-21 | survey fresh water | done | waiting SMS actual, fac hoc
111 | 4188686 - 2nd | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi final, SWCR | 2021-12-06 |  | Tunu 2nd | sirkulate
112 | 4227542 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi final & SWCR | 2021-12-06 |  | Bundwall
113 | 4188686 - 2nd phase 2 | SMS Estimate BOQ | 2021-12-06 |  | add Tunu phase 2
114 | 4223868 | SMS Actual, BOQ, FAC, HOC, weekly, monthly, claim, timesheet & dokumentasi final, SWCR | 2021-12-06 |  | Sirap 1st | sirkulate
115 | 7258712 | SMS Estimasi | 15/6/2021 |  | M3 pit flare | sirkulate
116 | 4227601 | SMS Estimasi | 15/6/2021 |  | Clinik
117 | 4226400 | SMS actual, BOQ,SWCR,FAC,HOC,natif wo |  | 18/06/2021 | HFA | Done
118 | 7246456 | SMS actual,BOQ,SWCR,FAC,HOC,Deductinal note,natif WO, timesheet & summary progress |  | 18/06/2021 | Handil 4 | Done
119 | 4227417 | SMS actual,BOQ,SWCR,FAC,HOC,natif WO, timesheet & summary progress |  | 18/06/2021 | hgl | Done
120 | 4221650 | SMS actual,BOQ,SWCR,FAC,HOC,natif WO, timesheet & summary progress |  | 18/06/2021 | BSB #2nd | Done
121 | 4221038 | HOC Approval |  | 18/06/2021 | HY | Done
122 | 7272018 | SMS actual,BOQ,natif WO,SWCR,HOC,FAC |  | 18/06/2021 | HA trimming | Done
123 | 7265133 | SMS Actual,BOQ,SWCR,Natif,HOC,FAC |  | 18/06/2021 | HGD gas bottle | Done
124 | 4188686 | SMS Actual,BOQ,Summary progress |  | 18/06/2021 | fasad 1st SMS | Done
125 | 4222976 | Natif Wo Approval |  | 18/06/2021 | HGL Swichgear | Done
126 | 7261453 | SMS Actual Approval |  | 18/06/2021 | HZC-HKA | Done
127 | 4193363 | SMS Actual,BOQ,SWCR,Natif,FAC,HOC |  | 18/06/2021 | HFA | Done
128 | 4193363 | SMS Actual,BOQ,SWCR,Natif,FAC,HOC |  | 18/06/2021 | HFA | Done
129 | 4204886 | FAC,HOC Approval |  | 18/06/2021 | Site survey fresh water | Done
130 | 4188686 - 2nd | SMS actual,BOQ,FAC,HOC,Deductinal note,natif WO & summary progress | 22/06/21 |  | Tunu phase 2
131 | 7258712 | SMS actual,BOQ,FAC,HOC,Deductinal note,natif WO & summary progress | 22/06/21 |  | M3 pit flare
132 | 4224696 | SMS actual,BOQ,FAC,HOC,natif WO,summary progress, Timehseet & dokumentasi | 26/06/21 |  | HS
133 | 4227542 | SMS actual,BOQ,FAC,HOC,natif WO,summary progress,SWCR, Timehseet & dokumentasi | 30/06/21 |  | cleaning ditch
Juli
134 | 4226290 | SMS Initial phase 1, SWCR,resum,time sheet, daily report, summary progress |  | 2021-07-07 | Transit pit - phase 1 (revisi add) |  | Done
135 | 7258712 | SMS actual, SWCR,resume, time sheet, daily report, summary progress |  | 2021-07-07 | M3 Pit | Done (SMS initial belum kembali
136 | 4223868 | SMS actual,SWCR,HOC,FAC,Daily activities & Report,Summary progress, dokumentasi (final summary) |  | 2021-09-07 | Sirap 1st | Done
137 | 4188686 | SMS actual,SWCR,HOC,FAC,Daily activities & Report,Summary progress, dokumentasi (final summary) |  | 2021-09-07 | fasad 2nd | Done
138 | 4226646 | Summary Progress partial ke 1 | 2021-12-07 | 27/7/2021 | Miscellaneous | partial ke 1
139 | 4224348 | Summary Progress partial ke 1, timesheet & daily report | 2021-12-07 | 27/7/2021 | Pipe yard zona A | partial ke 1
140 | 4224348 - 6th | Summary Progress partial ke 2, timesheet & daily report | 2021-12-07 | 27/7/2021 | Pipe yard zona F | partial ke 2
141 | 4188686 - 3rd | Summary Progress partial ke 2, timesheet & daily report | 2021-12-07 | 27/7/2021 | siraf tambora | partial ke 1
142 | 4188686 - 3rd | Summary Progress partial ke 2, timesheet & daily report | 2021-12-07 | 27/7/2021 | Fasad tambora | partial ke 1
143 | 4227476 | SMS actual,BQ,FAC,HOC,SWCR,Sumari Progress,Timesheet actual dokumentasi |  | 27/7/2021 | HS caterpilar | Done
144 | 4224696 | SMS actual,BQ,FAC,HOC,SWCR,Sumari Progress,Timesheet actual dokumentasi |  | 27/7/2021 | HS caterpilar | Done
145 | 4223227 | SMS Estimasi,BQ,Drawing |  | 27/7/2021 | PWK Shelter 21 #3rd | Done
146 | 4223227 | SMS Estimasi,BQ,Drawing |  | 27/7/2021 | PWK Shelter 21 #2nd | Done
Agustus
147 | 4300550 | SMS actual,BOQ,natif WO,SWCR,HOC,FAC,summary progress, daily activitie dan timesheet | 2021-05-08 |  | HN clearing #1st
148 | 4224348 | Summary progress, time sheet & daily activities ke 2 | 2021-05-08 |  | Pipe yard #1st | cancel
149 | 4300398 | SMS actual,BOQ,natif WO,SWCR,HOC,FAC,summary progress, daily activitie dan timesheet | 2021-05-08 |  | HNA sandbags
150 | 4224348 | Summary progress, time sheet & daily activities ke 1 | 2021-07-08 |  | Pipe yard #2nd | cancel
151 | 4224348 | Summary progress, time sheet & daily activities ke 1 | 2021-07-08 |  | Pipe yard #7st | cancel
152 | 4188686 - 2nd | SMS actual,BOQ,FAC,HOC,,natif WO & summary progress |  | 18/08/2021 | Tunu phase 2 | Done
153 | 4223868 | SMS Estimasi |  | 18/08/2021 | Sirap #3rd | Done
154 | 41886886 | SMS Estimasi approve |  | 18/08/2021 | Cinema room fasat #5st | Done
155 | 4300550 | SMS actual,BQ,FAC,HOC,SWCR,Sumari Progress,Timesheet actual dokumentasi |  | 18/08/2021 | HN #1st | Done
156 | 4227542 | SMS actual,BQ,FAC,HOC,SWCR,Sumari Progress,Timesheet actual dokumentasi |  | 18/08/2021 | Sediment cleaning | Done
September
157 | 4224348 - 7th | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 | 7/92021 | Zona G | resubmite weekly dan monthly (belum di sign)
158 | 4224348 - 1st | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 dan ke 2 | 2021-04-09 | 7/92021 | Zona A | done
159 | 4224348 - 2nd | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 | 7/92021 | Zona B | done
160 | 4224348 - 3rd | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 | 7/92021 | Zona C | done
161 | 4224348 - 4st | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 | 7/92021 | Zona D | done
162 | 4224348 - 5st | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 | 7/92021 | Zona E | done
163 | 4301260 | SMS actual,BOQ,natif WO,HOC,FAC,summary progress, daily activitie dan timesheet | 2021-04-09 |  | HN - Asst 8" piping
164 | 4228201 - 2nd | SMS actual,BOQ,natif WO,HOC,FAC,summary progress, daily activitie dan timesheet | 2021-04-09 |  | HN Cleaning
165 | 4227601 | Summary weekly,monthly,claim, dokumentasi, timesheet ke-1 | 2021-04-09 |  | CPA CR
166 | 4300550 - 3rd | SMS actual,BOQ,natif WO,HOC,FAC,summary progress, daily activitie dan timesheet | 2021-04-09 |  | HN Cutting
167 | 4300260 | SMS actual,BOQ,natif WO,FAC,summary progress, daily activitie dan timesheet, deductional note |  | 2021-07-09 | barge hooper | resubmited HOC (belum kembali)
168 | 4222912 | SMS actual,BOQ,natif WO,FAC,summary progress,HOC,SWCR |  | 2021-07-09 | pipe yard barbed | belum kembali timesheet dan daily activities
169 | 210397/VH | SWCR |  | 2021-07-09 | cleaning HN | Done
170 | 21036/VH | SWCR |  | 2021-07-09 | cutting trees HN | Done
171 | 210398/VH | SWCR |  | 2021-07-09 | HEA | Done

## CRO Req List SPS-PWK
No. | No. Work Order | No. CRO. Lama. | No. CRO Baru. | Job Description | Status SMS | Estimate / Internal SMS (Value) | Total Progress (Value) | % | Job Status | Total Invoice Previous Month | Invoice This Month | Remark | Updated
PERIODE JULI
1 | 4225051 |  | 3700065881 | [6 empty] | 0
PERIODE AGUSTUS
1 | 4225051 - 2nd |  | 3700065589 | [6 empty] | 0
PERIODE SEPTEMBER
1 | 4227818 |  | 3700065592 | [6 empty] | 0
2 | 4223227 | [8 empty] | 0
3 | 4223227 - 2nd | [8 empty] | 0
4 | 4223227 - 3rd | [8 empty] | 0
| 4227423 | [8 empty] | 0

## CRO Req List HCA
No. | No. Work Order | No Item. | No. CRO. Lama. | No. CRO Baru. | Job Description | Status SMS | Estimate / Internal SMS (Value) | Total Progress (Value) | % | Job Status | Total Invoice Previous Month | Invoice This Month | Remark | Updated
PERIODE JULI
1 | 4204886 | 190285/VC |  | 3700066074
2 | 7246456 | 190428/VH |  | 3700066075
3 | 4226400 | 210236/VH |  | 3700066076
4 | 4226526 | 210247/VH |  | 3700066455
5 | 4213148 | 190827/VH |  | 3700066109
6 | 4226822 | 210262/VH |  | 3700066077
7 | 4224348 - 6th | 210002/VHB |  | 3700066095 | [7 empty] | 102564269
8 | 4193363 | 180341/VH |  | 3700066096
9 | 4226931 | 210269/VHB |  | 3700066104
10 | 7272018 | 210218/VH |  | 3700066108
11 | 4227417 | 210315/VC |  | 3700066059
12 | 4221650 - 2nd | 200483/VC |  | 3700066060
PERIODE AGUSTUS
1 | 4188686 - 2nd | 180017/VH |  | 3700066456 | [6 empty] | 411620649 | 35753830 | Sisa nilai CRO lama
2 | 4188686 - 3rd | 180017/VH |  | 3700066180 | [7 empty] | 356601241
3 | 4223868 | 200634/VHB |  | 3700066457 | [6 empty] | 394860562 | 96376145 | Sisa nilai CRO lama
4 | 4224348 | 210002/VHB |  | 3700066181 | [7 empty] | 427919395
5 | 4226646 | 210251/VC |  | 3700066183 | [7 empty] | 136319448
6 | 4224348 - 6th | 210002/VHB |  | 3700066095 | [6 empty] | 102564268 | 81535613
7 | 4223868 - 2nd | 200634/VHB |  | 3700066185 | [7 empty] | 439790680
8 | 4226290 | 210231/VC |  | 3700066211
9 | 4224696 | 210039/VH |  | 3700066212
10 | 4227476 | 210318/VH |  | 3700066217
11 | 7258712 | 200140/VC |  | 3700066187
PERIODE SEPTEMBER
1 | 4205596 | 190326/VHB | [10 empty] | Menunggu HOC & Punch list closing
2 | 4211905 | SUB 19289/VC | [8 empty] | 5089483736 |  | Menunggu HOC & aktual kalkulasi dari team ENG
3 | 4222976 | 200568/VC |  | 3700066736 | [8 empty] | Plan Sep
4 | 4216521 | 200092/VHB
5 | 7265133 | 200476/VH
6 | 7260027 | 200216/VH |  | SMS Internal Circulate
7 | 4222912 | 200570/VHB | [11 empty] | Submited SMS Internal
8 | 4219719 | 200344/VH
9 | 4207186 | 190462/VH
| 4224348 | 210002/VHB |  | 3700066181 | [6 empty] | 427919395 | 277606580 | Plan Sep
10 | 4224348 - 2nd | 210002/VHB |  | 3700066742 | [7 empty] | 170327675 | Plan Sep
11 | 4224348 - 3rd | 210002/VHB |  | 3700066749 | [7 empty] | 37078145 | Plan Sep
12 | 4224348 - 4th | 210002/VHB |  | 3700066782 | [7 empty] | 213226848 | Plan Sep
13 | 4224348 - 5th | 210002/VHB |  | 3700066801 | [7 empty] | 258878731 | Plan Sep
14 | 4224348 - 7th | 210002/VHB |  | 3700066805 | [7 empty] | 341130563 | Plan Sep
15 | 4227542 | 210327/VHB |  | 3700066658 | [7 empty] | 85778350 | Plan Sep | Submited SMS Internal
16 | 4227601 | 21330/VC | [10 empty] | Plan Sep | Submited SMS Internal
17 | 4188686 - 2nd - Phase 2 | 180017/VH |  | 3700066816 | [7 empty] | 130011815 | Plan Sep
18 | 4228201 | 210362/VH | [11 empty] | Submited SMS Internal
19 | 4217251 | 200139/VC
20 | 4300260 | 210378/VHB |  | 3700066817 | [8 empty] | Plan Sep
21 | 4223868 - 3rd | 200634/VB
22 | 4188686 - 5rd | 180017/VH
23 | 4300398 | 210380/VH |  | 3700066652 | [8 empty] | Plan Sep
24 | 4300550 | 210397/VH |  | 3700066669 | [8 empty] | Plan Sep
25 | 210398/VH | 210398/VH | [11 empty] | Submited SMS Internal
26 | 4225908 | 210186/VHB | [10 empty] | Dokumen sirkulasi (nilai actual = 4225908 + 4225908 - phase 2) done | Submited SMS Internal
| 4225908 - Phase 2 | 210186/VHB | [10 empty] | Dokumen sirkulasi (nilai actual = 4225908 + 4225908 - phase 2) done | Submited SMS Internal
27 | 4228201 - 2nd | 210362/VH |  | 3700068120 | [9 empty] | Submited SMS Internal
28 | 4300550 - 3rd | 210397/VH |  | 3700068119 | [9 empty] | Submited SMS Internal
29 | 4301260 | 210448/VH |  | 3700068180 | [9 empty] | Submited SMS Internal
Total Rencana Invoice